## Sheet1
Triangle Site External Works
| SW2 Enterprise Centre |  |  |  |  | GIFA
7650
| Description | Quantity | Unit | Rate | Total
External Works
No allowance made for cut and fill
| Allowance to break out top course tarmac and pavement on Porden Rd | 1155 | m² | 40 | 46200
0
| Allowance for site strip | 2225 | m² | 5 | 11125
0
| Granite sett paving with sub-base | 1380.48 | m² | 110 | 151852.8
0
| Allowance for inset lighting to feature paving | 1 | unit | 50000 | 50000
0
| Concrete sett paving | 1154.88 | m² | 55 | 63518.4
0
| Allowance for Sculpture Garden artworks | 274.56 | m² | 120 | 32947.2
0
| Small street tree planting | 10 | nr | 750 | 7500
0
| Benches | 18 | nr | 500 | 9000
0
| Hydraulic bollards | 2 | nr | 2000 | 4000
0
| Large street tree planting | 13 | nr | 2000 | 26000
0
| Meadow roof terrace | 115.2 | m² | 200 | 23040
0
| Crèche play | 1 | Item | 20000 | 20000
0
| Pedestrian bollards | 14 | nr | 250 | 3500
0
| Allowance for junction works | 2 | nr | 30000 | 60000
0
| Allowance for pavement reinstatement works | 368 | m | 105 | 38640
0
| Kerb detail, specification tbc | 259.2 | m | 50 | 12960
0
| Residential courtyard surfacing | 376 | m2 | 80 | 30080
0
| Allowance for miscellaneous planting | 1 | item | 15000 | 15000
0
| Allowance for drainage upgrade works | 1 | item | 500000 | 500000
0
| Allowance for services reinforcement and upgrade | 1 | item | 250000 | 250000
0
| Allowance for service connections to all buildings on triangle site. | 1 | item | 350000 | 350000
0
| CCTV to Town Hall, Ivor House and New office external areas | 1 | item | 60000 | 60000
| Preliminaries |  |  |  | 0
0
| @ | 14 | % | 1765363.4 | 247150.876
0
| Allowance for Design Fees |  |  |  | 0
0
| @ | 9.575 | % | 2012514.276 | 192698.2419
0
| Overheads & Profit |  |  |  | 0
0
| @ | 7 | % | 2205212.5179 | 154364.8763
0
0
0
|  |  |  | Sub-Total | 2359577.3942
|  |  |  | Add contingency of 10% | 235957.7394
|  |  |  | Total | 2595535.1336
Assumptions
1
2
3
4
5
6
7
8
9
10