## Sheet1
CENTRAL AREA
YEAR 4 STREETS PROGRAMME
PROPERTY ADDRESS : | 16 St Johns Crescent
SCAFFOLDING
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Scaffolding: Provide, erect and dismantle tubular scaffolding, with ladders, pulley ropes, wheel fixings etc. | [8 empty] | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
a | 5.00m high - 8 weeks hire |  | m² | 13.344 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | 10.00m high - 10 weeks hire |  | m² | 11.398 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
c | 15.00m high - 13 weeks hire | 700 | m² | 13.9 | 9730 | 700 | 9730 | 100% | 9730 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
d | 20.00m high - 13 weeks hire |  | m² | 12.51 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
e | Provide access to Chimney stacks for rebuilding or repair; up to 2m high | 1 | Nr | 500 | 500 | 1 | 500 | 100% | 500 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
f | Additional weekly hire (allow 26 weeks total for blocks) |  | m² | 0.9 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
2 | Scaffolding: Provide, erect, maintain for a period not exceeding one week and dismantle tubular tower scaffolding with all ladders, pulley rope, wheel fixings and one lift of boards. | [8 empty] | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
a | ne 10.00m high |  | Nr | 480 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | ne 15.00m high |  | Nr | 800 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
c | ne 20.00mm high |  | Nr | 1371 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
d | Move tubular tower scaffolding to new location as directed by Contract Administrator, temporary dismantle and re-erect as necessary, any height of tower. |  | Nr | 83.67 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
3 | Provide scissor lift or telescopic hydraulic platform vehicle, max capacity 200kg up to 10.00m platform height, attend upon CA during inspection, with any temporary relocation, remove. | [8 empty] | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
a | 10m High |  | Days | 29.1 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | 20m High |  | Days | 29.1 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
4 | Protection | [8 empty] | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
a | Debris netting |  | m² | 0.01 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | Provide, erect and maintain dust proof external screen, remove. | 700 | m² | 2 | 1400 | 700 | 1400 | 100% | 1400 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
c | 3 metre wide protective fan over communal entrances | 6 | m² | 16.67 | 100.02 | 6 | 100.02 | 100% | 100.02 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
d | Brick Guards | 10 | m | 0.5 | 5 | 10 | 5 | 100% | 5 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
e | Temporary Guard rails to plant rooms/lift shaft/stairwells |  | m | 15 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
5 | Provide, erect, maintain for a period n.e. one week, dismantle, flexible plastic, standard size rubbish chute fixed to scaffold; complete with siteguard panels, side entry chute. | [8 empty] | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
a | ne 10.00m high |  | m | 32 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | ne 15.00m high | 30 | m | 32 | 960 | 30 | 960 | 100% | 960 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
c | ne 20.00m high |  | m | 36 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
6 a | 300kg electric goods hoist seving up to 9 storeys high; including erection, testing, 13 weeks hire, power supply, all electricity, 2 metre high 'Heras' fencing. enclosure and dismantling | 1 | Nr | 2388 | 2388 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
b | Additional weekly hire |  | weeks | 191 | 0 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
7 | 2 metre high 'Heras fencing to perimeter of ground/1st floor scaffold | 10 | m | 9 | 90 | 10 | 90 | 100% | 90 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
8 | Scaffold alarm to perimeter at 1st floor level for 28 day period; including installation and dismantling, warning signs to each elevation, 2 pairs of dual-tech beams and control via a keyholding company. | 1 | Nr | 400 | 400 |  | 0 |  | 0 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
|  |  |  | SECTION TOTAL | 15573.02 |  | 12785.02 |  | 12785.02
DOMESTIC PLUMBING WORKS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
Above Ground Drainage
9 | Soil Stacks
a | Take down external soil stack complete to any dwelling over 2 but n.e. 4 storeys; renew with 110mm PVCu pipework including all fittings, joints, fixing to structure, making good & testing. |  | m | 19 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
b | Renew 110mm diameter PVCu length or section of internal soil stack; including all fixings & clips, joints, making good, removal & refixing of duct casings and testing. |  | m | 23.75 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
c | Extra over for replacement in cast iron. |  | m | 23.75 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
10 | Gutters & Downpipes |  |  |  | 0 |  | 0 |  | 0
a | 112mm PVCu gutter of any profile; including support brackets, angles, outlets, stop ends, cutting, lining & levelling, connections to existing guttering & downpipes. |  | m | 8.55 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
b | 150mm PVCu gutter of any profile; including support brackets, angles, outlets, stop ends, cutting, lining & levelling, connections to existing guttering & downpipes. | 40 | m | 9.5 | 380 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
c | Extra over for replacement in cast iron. |  | m | 11.875 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
d | Renew round or square PVCu downpipe to any dwelling over 2 but n.e. 4 storeys; including new brackets, branches, offsets, hopper head, shoe, terminal, slate, joints & making good. | 60 | m | 8.55 | 513 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
e | Extra over for replacement in cast iron. |  | m | 24.225 | 0 |  | 0 |  | 0 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal
Associated Asbestos works are covered in a separate section of this document
|  |  |  | SECTION TOTAL | 893 |  | 0 |  | 0
COMMUNAL LIGHTING
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
CL1 | Supply and install three compartment 150 x 50mm steel galvanised trunking from both electrical intakes rising up the stairwell to the roof space and along all undersides of balconies. Trunking to be wireway for landlords lighting, door entry and communal aerial cabling. |  | Storeys | 928 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL2 | Landlords lighting shall be wired through the new three compartment trunking in 1.5mm² PVC single-stranded cable. Lighting shall be controlled from the controlled landlords distribution board. |  | m | 0.55 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL3 | Supply and install new fittings on the underside of the public balconies (Coughtrie CPS 28-2D (large) or equivalent specification) which shall be fed via HG galvanised steel conduit fed from the new three compartment trunking. |  | nr | 133.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL4 | Supply and install new fittings to stairwells (Coughtrie CPS 28-2D (large) or equivalent specification) which shall be fed via HG galvanised steel conduit fed from the new three compartment trunking. |  | nr | 133.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL5 | Supply and install new fittings to electrical intake cupboards (Coughtrie CPS 28-2D (large) or equivalent specification) which shall be fed via HG galvanised steel conduit fed from the new three compartment trunking including the provision of an independent switch control. |  | nr | 160.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL6 | Supply and install wall-packette fittings (70W Holophane or equivalent approved) to entrances and front and sides externally fed by 1.5mm² M.I.C.C. cable wiring. |  | nr | 275 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL7 | Supply and install new Timeswitch Quartz controlled solar dial zone 2 (Sangamo controls or equivalent specification) complete with box for conduit entry. |  | nr | 5.43 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
Capital SOR ¦ Electrical Installations ¦ Communal Lighting
CL8 | External bulkhead light with photo-cell and internal switch. |  | nr | 29 | 0 |  | 0 |  | 0 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting
|  |  |  | SECTION TOTAL | 0 |  | 0 |  | 0
LIGHTNING CONDUCTOR
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
Supply and install the following including all labour, plant, materials, making good, builders work etc and with full cognisance of the expanded detail relating to items on this page provided on the attached, related specification.
LC1 | Supply and install lightning conductor system including all fixings, clips, joints, terminals, clamps and earthing rods all in accordance with the requirements set out in the lightning protection specification and also allow for bonding ladders, rails, communal aerial masts and poles to earth. |  | m | 6 | 0 |  | 0 |  | 0 | Capital SOR ¦ Lightning Protection ¦ Lightning Protection System - Renewal
LC2 | Test and commission lightning protection system including demonstrations and provision of all commissioning sheets and certificates, installed drawings and technical materials. |  | Nr | 300 | 0 |  | 0 |  | 0 | Capital SOR ¦ Lightning Protection ¦ Lightning Protection System - Renewal
|  |  |  | SECTION TOTAL | 0 |  | 0 |  | 0
UPVC WINDOWS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
UPVC
| Carry out conditions survey including photographic record to property before works commence for uPVC windows |  | Nr | 0 | 0 |  | 0 |  | 0
| Take down or disconnect any security grilles, wires, alarms, nets, curtains and battens to facilitate removal and installation of windows; re-connect wiring and alarms and re-fix battens, nets and curtains. |  | prop | 0 | 0 |  | 0 |  | 0
a | uPVC Windows, fixed pane 400 x 600 |  | Nr | 64.7108 | 0 |  | 0 |  | 0
b | uPVC Windows, fixed pane 400 x 800 |  | Nr | 69.0983 | 0 |  | 0 |  | 0
c | uPVC Windows, fixed pane 600 x 800 |  | Nr | 75.3675 | 0 |  | 0 |  | 0
d | uPVC Windows, fixed pane 600 x 1000 |  | Nr | 82.0755 | 0 |  | 0 |  | 0
e | uPVC Windows, fixed pane 800 x 1000 |  | Nr | 88.9688 | 0 |  | 0 |  | 0
f | uPVC Windows, fixed pane 1000 x 1000 |  | Nr | 112.3005 | 0 |  | 0 |  | 0
g | uPVC Windows, fixed pane 1200 x 1000 |  | Nr | 131.3227 | 0 |  | 0 |  | 0
h | uPVC Windows, fixed pane 1400 x 1000 |  | Nr | 128.8852 | 0 |  | 0 |  | 0
i | uPVC Windows, fixed pane 1600 x 1000 |  | Nr | 146.9325 | 0 |  | 0 |  | 0
j | uPVC Windows, fixed pane 1800 x 1000 |  | Nr | 154.9275 | 0 |  | 0 |  | 0
k | uPVC Windows, fixed pane 2000 x 1000 |  | Nr | 167.9145 | 0 |  | 0 |  | 0
l | uPVC Windows, fixed pane 1200 x 2000 |  | Nr | 187.3462 | 0 |  | 0 |  | 0
m | uPVC Windows, fixed pane 1400 x 2000 |  | Nr | 202.9365 | 0 |  | 0 |  | 0
n | uPVC Windows, fixed pane 1600 x 2000 |  | Nr | 222.027 | 0 |  | 0 |  | 0
o | uPVC Windows, fixed pane 1800 x 2000 |  | Nr | 231.6795 | 0 |  | 0 |  | 0
p | uPVC Windows, fixed pane 2000 x 2000 |  | Nr | 270.0945 | 0 |  | 0 |  | 0
q | uPVC Windows, fixed pane 2200 x 2000 |  | Nr | 285.3533 | 0 |  | 0 |  | 0
a | uPVC Windows, Casement 400 x 600 |  | Nr | 99.5378 | 0 |  | 0 |  | 0
b | uPVC Windows, Casement 400 x 800 |  | Nr | 104.9002 | 0 |  | 0 |  | 0
c | uPVC Windows, Casement 600 x 800 |  | Nr | 112.0568 | 0 |  | 0 |  | 0
d | uPVC Windows, Casement 600 x 1000 |  | Nr | 119.9348 | 0 |  | 0 |  | 0
e | uPVC Windows, Casement 800 x 1000 |  | Nr | 128.8268 | 0 |  | 0 |  | 0
f | uPVC Windows, Casement 1000 x 1000 |  | Nr | 142.5938 | 0 |  | 0 |  | 0
g | uPVC Windows, Casement 1200 x 1000 |  | Nr | 164.6482 | 0 |  | 0 |  | 0
h | uPVC Windows, Casement 1400 x 1000 |  | Nr | 182.8028 | 0 |  | 0 |  | 0
i | uPVC Windows, Casement 1600 x 1000 |  | Nr | 196.0823 | 0 |  | 0 |  | 0
j | uPVC Windows, Casement 1800 x 1000 |  | Nr | 203.9992 | 0 |  | 0 |  | 0
k | uPVC Windows, Casement 2000 x 1000 |  | Nr | 210.9412 | 0 |  | 0 |  | 0
l | uPVC Windows, Casement 1200 x 2000 |  | Nr | 244.5593 | 0 |  | 0 |  | 0
m | uPVC Windows, Casement 1400 x 2000 |  | Nr | 260.2665 | 0 |  | 0 |  | 0
n | uPVC Windows, Casement 1600 x 2000 |  | Nr | 279.9518 | 0 |  | 0 |  | 0
o | uPVC Windows, Casement 1800 x 2000 |  | Nr | 294.5962 | 0 |  | 0 |  | 0
p | uPVC Windows, Casement 2000 x 2000 |  | Nr | 318.4837 | 0 |  | 0 |  | 0
q | uPVC Windows, Casement 2200 x 2000 |  | Nr | 336.5212 | 0 |  | 0 |  | 0
a | uPVC Windows, Tilt and Turn 400 x 600 |  | Nr | 153.1627 | 0 |  | 0 |  | 0
b | uPVC Windows, Tilt and Turn 400 x 800 |  | Nr | 162.4253 | 0 |  | 0 |  | 0
c | uPVC Windows, Tilt and Turn 600 x 800 |  | Nr | 170.5567 | 0 |  | 0 |  | 0
d | uPVC Windows, Tilt and Turn 600 x 1000 |  | Nr | 181.3597 | 0 |  | 0 |  | 0
e | uPVC Windows, Tilt and Turn 800 x 1000 |  | Nr | 193.1767 | 0 |  | 0 |  | 0
f | uPVC Windows, Tilt and Turn 1000 x 1000 |  | Nr | 210.8438 | 0 |  | 0 |  | 0
g | uPVC Windows, Tilt and Turn 1200 x 1000 |  | Nr | 234.3607 | 0 |  | 0 |  | 0
h | uPVC Windows, Tilt and Turn 1400 x 1000 |  | Nr | 246.1778 | 0 |  | 0 |  | 0
i | uPVC Windows, Tilt and Turn 1600 x 1000 |  | Nr | 258.9698 | 0 |  | 0 |  | 0
j | uPVC Windows, Tilt and Turn 1800 x 1000 |  | Nr | 269.3243 | 0 |  | 0 |  | 0
k | uPVC Windows, Tilt and Turn 2000 x 1000 |  | Nr | 279.1913 | 0 |  | 0 |  | 0
l | uPVC Windows, Tilt and Turn 1200 x 2000 |  | Nr | 320.1217 | 0 |  | 0 |  | 0
m | uPVC Windows, Tilt and Turn 1400 x 2000 |  | Nr | 341.1915 | 0 |  | 0 |  | 0
n | uPVC Windows, Tilt and Turn 1600 x 2000 |  | Nr | 364.2892 | 0 |  | 0 |  | 0
o | uPVC Windows, Tilt and Turn 1800 x 2000 |  | Nr | 390.5362 | 0 |  | 0 |  | 0
p | uPVC Windows, Tilt and Turn 2000 x 2000 |  | Nr | 418.3433 | 0 |  | 0 |  | 0
q | uPVC Windows, Tilt and Turn 2200 x 2000 |  | Nr | 437.307 | 0 |  | 0 |  | 0
|  |  |  | SECTION TOTAL | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
TIMBER WINDOWS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
| Carry out conditions survey including photographic record to property before works commence |  | Nr | 0 | 0 |  | 0 |  | 0
| Take down or disconnect any security grilles, wires, alarms, nets, curtains and battens to facilitate removal and installation of windows; re-connect wiring and alarms and re-fix battens, nets and curtains. |  | Prop | 0 | 0 |  | 0 |  | 0
a | Timber Windows, fixed pane 400 x 600 |  | Nr | 117.78 | 0 |  | 0 |  | 0
b | Timber Windows, fixed pane 400 x 800 |  | Nr | 123.162 | 0 |  | 0 |  | 0
c | Timber Windows, fixed pane 600 x 800 |  | Nr | 132.7463 | 0 |  | 0 |  | 0
d | Timber Windows, fixed pane 600 x 1000 |  | Nr | 155.3175 | 0 |  | 0 |  | 0
e | Timber Windows, fixed pane 800 x 1000 |  | Nr | 168.0412 | 0 |  | 0 |  | 0
f | Timber Windows, fixed pane 1000 x 1000 |  | Nr | 180.726 | 0 |  | 0 |  | 0
g | Timber Windows, fixed pane 1200 x 1000 |  | Nr | 193.5765 | 0 |  | 0 |  | 0
h | Timber Windows, fixed pane 1400 x 1000 |  | Nr | 206.271 | 0 |  | 0 |  | 0
i | Timber Windows, fixed pane 1600 x 1000 |  | Nr | 213.9832 | 0 |  | 0 |  | 0
j | Timber Windows, fixed pane 1800 x 1000 |  | Nr | 225.1275 | 0 |  | 0 |  | 0
k | Timber Windows, fixed pane 2000 x 1000 |  | Nr | 236.2035 | 0 |  | 0 |  | 0
l | Timber Windows, fixed pane 1200 x 2000 |  | Nr | 252.018 | 0 |  | 0 |  | 0
m | Timber Windows, fixed pane 1400 x 2000 |  | Nr | 272.7757 | 0 |  | 0 |  | 0
n | Timber Windows, fixed pane 1600 x 2000 |  | Nr | 335.0295 | 0 |  | 0 |  | 0
o | Timber Windows, fixed pane 1800 x 2000 |  | Nr | 355.6898 | 0 |  | 0 |  | 0
p | Timber Windows, fixed pane 2000 x 2000 |  | Nr | 376.3403 | 0 |  | 0 |  | 0
q | Timber Windows, fixed pane 2200 x 2000 |  | Nr | 397.1565 | 0
a | Timber Windows, Casement 400 x 600 |  | Nr | 177.885 | 0 |  | 0 |  | 0
b | Timber Windows, Casement 400 x 800 |  | Nr | 187.326 | 0 |  | 0 |  | 0
c | Timber Windows, Casement 600 x 800 |  | Nr | 199.53 | 0 |  | 0 |  | 0
d | Timber Windows, Casement 600 x 1000 | 1 | Nr | 218.637 | 218.637 |  | 0 |  | 0
e | Timber Windows, Casement 800 x 1000 |  | Nr | 232.029 | 0 |  | 0 |  | 0
f | Timber Windows, Casement 1000 x 1000 |  | Nr | 285.57 | 0 |  | 0 |  | 0
g | Timber Windows, Casement 1200 x 1000 |  | Nr | 296.154 | 0 |  | 0 |  | 0
h | Timber Windows, Casement 1400 x 1000 |  | Nr | 359.73 | 0 |  | 0 |  | 0
i | Timber Windows, Casement 1600 x 1000 |  | Nr | 433.809 | 0 |  | 0 |  | 0
j | Timber Windows, Casement 1800 x 1000 |  | Nr | 445.455 | 0 |  | 0 |  | 0
k | Timber Windows, Casement 2000 x 1000 |  | Nr | 479.313 | 0 |  | 0 |  | 0
l | Timber Windows, Casement 1200 x 2000 |  | Nr | 505.251 | 0 |  | 0 |  | 0
m | Timber Windows, Casement 1400 x 2000 |  | Nr | 531.171 | 0 |  | 0 |  | 0
n | Timber Windows, Casement 1600 x 2000 |  | Nr | 548.1 | 0 |  | 0 |  | 0
o | Timber Windows, Casement 1800 x 2000 |  | Nr | 565.029 | 0 |  | 0 |  | 0
p | Timber Windows, Casement 2000 x 2000 |  | Nr | 592.317 | 0 |  | 0 |  | 0
q | Timber Windows, Casement 2200 x 2000 |  | Nr | 608.625 | 0 |  | 0 |  | 0
a | Timber Windows, Tilt and Turn 400 x 600 |  | Nr | 273.429 | 0 |  | 0 |  | 0
b | Timber Windows, Tilt and Turn 400 x 800 |  | Nr | 289.224 | 0 |  | 0 |  | 0
c | Timber Windows, Tilt and Turn 600 x 800 |  | Nr | 309.879 | 0 |  | 0 |  | 0
d | Timber Windows, Tilt and Turn 600 x 1000 |  | Nr | 322.497 | 0 |  | 0 |  | 0
e | Timber Windows, Tilt and Turn 800 x 1000 |  | Nr | 333.711 | 0 |  | 0 |  | 0
f | Timber Windows, Tilt and Turn 1000 x 1000 |  | Nr | 347.742 | 0 |  | 0 |  | 0
g | Timber Windows, Tilt and Turn 1200 x 1000 |  | Nr | 479.736 | 0 |  | 0 |  | 0
h | Timber Windows, Tilt and Turn 1400 x 1000 |  | Nr | 493.596 | 0 |  | 0 |  | 0
i | Timber Windows, Tilt and Turn 1600 x 1000 |  | Nr | 508.608 | 0 |  | 0 |  | 0
j | Timber Windows, Tilt and Turn 1800 x 1000 |  | Nr | 521.514 | 0 |  | 0 |  | 0
k | Timber Windows, Tilt and Turn 2000 x 1000 |  | Nr | 549.783 | 0 |  | 0 |  | 0
l | Timber Windows, Tilt and Turn 1200 x 2000 |  | Nr | 577.008 | 0 |  | 0 |  | 0
m | Timber Windows, Tilt and Turn 1400 x 2000 |  | Nr | 599.832 | 0 |  | 0 |  | 0
n | Timber Windows, Tilt and Turn 1600 x 2000 |  | Nr | 623.016 | 0 |  | 0 |  | 0
o | Timber Windows, Tilt and Turn 1800 x 2000 |  | Nr | 645.876 | 0 |  | 0 |  | 0
p | Timber Windows, Tilt and Turn 2000 x 2000 |  | Nr | 683.118 | 0 |  | 0 |  | 0
q | Timber Windows, Tilt and Turn 2200 x 2000 |  | Nr | 705.816 | 0 |  | 0 |  | 0
a | Timber Windows, Vertical Sliders 400 x 600 |  | Nr | 361.53 | 0 |  | 0 |  | 0
b | Timber Windows, Vertical Sliders 400 x 800 |  | Nr | 377.325 | 0 |  | 0 |  | 0
c | Timber Windows, Vertical Sliders 600 x 800 |  | Nr | 397.512 | 0 |  | 0 |  | 0
d | Timber Windows, Vertical Sliders 600 x 1000 |  | Nr | 410.67 | 0 |  | 0 |  | 0
e | Timber Windows, Vertical Sliders 800 x 1000 |  | Nr | 421.2 | 0 |  | 0 |  | 0
f | Timber Windows, Vertical Sliders 1000 x 1000 |  | Nr | 435.24 | 0 |  | 0 |  | 0
g | Timber Windows, Vertical Sliders 1200 x 1000 |  | Nr | 566.865 | 0 |  | 0 |  | 0
h | Timber Windows, Vertical Sliders 1400 x 1000 |  | Nr | 580.905 | 0 |  | 0 |  | 0
i | Timber Windows, Vertical Sliders 1600 x 1000 |  | Nr | 634.125 | 0 |  | 0 |  | 0
j | Timber Windows, Vertical Sliders 1800 x 1000 |  | Nr | 618.642 | 0 |  | 0 |  | 0
k | Timber Windows, Vertical Sliders 2000 x 1000 | 27 | Nr | 713.421 | 19262.367 |  | 0 |  | 0
l | Timber Windows, Vertical Sliders 1200 x 2000 |  | Nr | 793.548 | 0 |  | 0 |  | 0
m | Timber Windows, Vertical Sliders 1400 x 2000 |  | Nr | 877.563 | 0 |  | 0 |  | 0
n | Timber Windows, Vertical Sliders 1600 x 2000 |  | Nr | 1053.063 | 0 |  | 0 |  | 0
o | Timber Windows, Vertical Sliders 1800 x 2000 |  | Nr | 1140.75 | 0 |  | 0 |  | 0
p | Timber Windows, Vertical Sliders 2000 x 2000 |  | Nr | 1228.5 | 0 |  | 0 |  | 0
q | Timber Windows, Vertical Sliders 2200 x 2000 |  | Nr | 1316.25 | 0 |  | 0 |  | 0
|  |  |  | SECTION TOTAL | 19481.004 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
EXTRA OVER WORKS FOR WINDOW INSTALLATIONS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Glass
a | 2 x 4mm toughened safety glass or 24mm 'Plastisol' panel |  | m² | 8.8822 | 0 |  | 0 |  | 0
b | 6.4mm laminated to outer pane | 40 | m² | 10.413 | 416.52 |  | 0 |  | 0
c | 4mm obscure |  | m² | 4.875 | 0 |  | 0 |  | 0
d | 6mm obscure | 16 | m² | 7.69 | 123.04 |  | 0 |  | 0
e | georgian bar insert |  | m² | 15.6 | 0 |  | 0 |  | 0
f | self-cleaning glass |  | m² | 14.63 | 0 |  | 0 |  | 0
2 | Cills etc
a | 95mm cill |  | m | 0.98 | 0 |  | 0 |  | 0
b | 150mm cill |  | m | 0.98 | 0 |  | 0 |  | 0
c | 180mm cill | 56 | m | 2.925 | 163.8 |  | 0 |  | 0
d | 225mm cill |  | m | 5.36 | 0 |  | 0 |  | 0
e | 16mm couplers and covers |  | m | 7.31 | 0 |  | 0 |  | 0
f | 20mm packers |  | m | 3.41 | 0 |  | 0 |  | 0
g | baypole and adaptors |  | m | 19.5 | 0 |  | 0 |  | 0
h | bay jacks |  | nr | 6.53 | 0 |  | 0 |  | 0
i | lining to box sash |  | m | 5.36 | 0 |  | 0 |  | 0
3 | Windowboards
a | 'cappit' windowboard |  | m | 6.34 | 0 |  | 0 |  | 0
b | windowboard including all mitres, end caps & intersections |  | m | 9.87 | 0 |  | 0 |  | 0
c | scrollboard |  | m | 5.85 | 0 |  | 0 |  | 0
4 | 180mm uPVC liner trim including all adhesive, mitres, end caps and intersections. |  | m | 4.88 | 0 |  | 0 |  | 0
5 | Extract Fan works
a | core drill hole through brickwork for fan |  | nr | 75 | 0 |  | 0 |  | 0
b | temporarily protect hole prior to installation of fan |  | nr | 0.5 | 0 |  | 0 |  | 0
Other
6 | Provide 2 folding-arm opener operator poles to each resident. |  | Item | 4.16 | 0 |  | 0 |  | 0
7 | 12.5 thick plasterboard, 3mm thick plaster and 2 coats of emulsion in patch repair to reveals including all preparation and beading. |  | m2 | 6 | 0 |  | 0 |  | 0
8 | 25 x 50mm curtain batten plugged and screwed to brickwork or concrete; prepare and paint with one coat primer, one undercoat and one gloss coat finish. |  | m | 0.5 | 0 |  | 0 |  | 0
|  |  |  | SECTION TOTAL | 703.36 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
DOOR INSTALLATIONS
ITEM | DESCRIPTION OF WORKS | QTY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1.1 | Carefully take out and remove from site existing * door and frame including quadrants, architraves, keeps, plates, hinges, chains etc, taking care not to damage the internal plaster line and make good all works disturbed; Install new 'secure-by-design' door; including multi-point lock, thumb-turn cylinder, all quadrants, architraves, ironmongery, cills, threshold or 15mm wheelchair access thresholds where necessary, mastic pointing and security screw fixings.
* The resident may choose from any 1 of the 4 door (and associated frame) styles/types illustrated below with extra over cost implication being as indicated in 1A1(і) to 5(іv) below.
Front Doors ( Door & Frame )
a | Composite front door and frame*; wood-grained finished frame and laminated double glazing (where applicable), chrome ironmongery comprising 180º viewer, handle, hinge bolts, numerals, knocker, chain, internal security cowl, anti-drill feature, letterplate and perimeter draught excluder. |  | nr | 430.3163 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
b | Hardwood Timber front door and frame* with laminated double glazing (where applicable), chrome ironmongery comprising 180º viewer, handle, hinge bolts, numerals, knocker, chain, internal security cowl, anti-drill feature, letterplate and perimeter draught excluder. |  | nr | 640 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
1.2 | Front Doors Extra Overs
Composite
a | ditto but ½ hour fire rated including closer |  | nr | 306.9787 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
b | (і) door with fixed toplight not exceeding 400mm high |  | nr | 107.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 123.7177 | 0 |  | 0 |  | 0
c | (і) door with fixed sidelight not exceeding 450mm high |  | nr | 107.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 123.7177 | 0 |  | 0 |  | 0
d | (і) door with fixed sidelight not exceeding 450mm high and toplight not exceeding 400mm high |  | nr | 107.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 123.7177 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| Timber | [8 empty] | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
e | ditto but ½ hour fire rated including closer |  | nr | 0 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
f | (і) door with fixed toplight not exceeding 400mm high |  | nr | 55 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 80 | 0 |  | 0 |  | 0
Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
g | (і) door with fixed sidelight not exceeding 450mm high |  | nr | 325 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 410 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
h | (і) door with fixed sidelight not exceeding 450mm high and toplight not exceeding 400mm high |  | nr | 365 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
| (іі) ditto but ½ hour fire rated with g.w. glazing and closer |  | nr | 480 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
1.3 | *extra over cost for alternative door type as illustrated below
(a) & (e) below should be Zero being the standard/least expensive type as priced above in 1 & 2
a | Composite Flush |  | nr | 0 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
b | Composite 6 panel, part-glazed |  | nr | 0 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
c | Composite 'Carolina' |  | nr | 0 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
d | Composite Twin-glazed |  | nr | 0 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
e | Timber Flush |  | nr |  | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
f | Timber 6 panel, part-glazed |  | nr | 20 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
g | Timber 'Carolina' |  | nr | 45 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
h | Timber Twin-glazed |  | nr | 45 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
2 | Rear Doors ( Door & Frame )
a | uPVC rear door and frame, half double-glazed |  | nr | 378.3 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal
b | ditto but with fixed sidelight not exceeding 450mm wide |  | nr | 511.875 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal
c | Hardwood Timber rear door and frame, half double-glazed |  | nr | 660 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal
d | ditto but with fixed sidelight not exceeding 450mm wide |  | nr | 985 | 0 |  | 0 |  | 0 | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal
|  |  |  | SECTION TOTAL | 0 |  | 0 |  | 0
ROOFING WORKS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Replace fascia and soffit boards in uPVC, including preparing sub-frame, 25mm strip ventilators, all drips, trims, seals, mastic pointing and scaffolding | [8 empty] | Capital SOR ¦ Roof Works ¦ Fascias and Soffits - Renewal
a | not exceeding 200mm wide |  | m | 12.1875 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Fascias and Soffits - Renewal
b | not exceeding 300mm wide | 40 | m | 16.0875 | 643.5 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Fascias and Soffits - Renewal
2 | Replace barge boards in uPVC, not exceeding 300; including preparing sub-frame, trimming of rafter ends, all drips, trims, seals, mastic pointing, making good to undercloak, pointing up in sand-cement and all scaffolding. |  | m | 17.55 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Fascias and Soffits - Renewal
3 | Strip off existing pitched roof coverings and remove from site; install new breathable felt, insulation, tanalised battens and same-weighted tiles/slates including vent tiles/slates, eaves vents, ridge tiles, hip tiles, all scaffolding and 'Ubiflex' flashings & soakers (or flashings & soakers of an equivalent specification) to stacks and abutments (all in accordance with manufacturers instructions). | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a(i) | Main roof and/or rear addition roof tiles |  | m² | 29.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
(ii) | Main roof and/or rear addition roof slates | 107 | m² | 175 | 18725 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b(i) | Hip end roof tiles |  | m² | 21.177 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
(ii) | Hip end roof slates | 24 | m² | 175 | 4200 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
c | Pediment (tiles/slate) |  | m² | 53.63 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
d(і) | 'Ubiflex' flashings and soakers (or flashings & soakers of an equivalent specification) to abutments |  | m | 34.125 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
(іі) | Replace lead stepped flashings and soakers to Chimney with 'Ubiflex' (or flashings & soakers of an equivalent specification); not exceeding 225mm girth; clean out groove of brickwork, wedge with lead and repoint in mastic including all necessary labours. |  | m | 39 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
e | Replace lead valley gutter with 'Ubiflex' (or gutters of an equivalent specification); n.e. 800mm girth; remove and refix roof tiles or slates and battens as required, including all necessary labours. |  | m | 58.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
4 | Replace roof tiles, including any scaffolding required | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a | single tile |  | nr | 6.825 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | patch repair |  | m² | 43.875 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
c | vent tile |  | nr | 58.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
d | hip tile |  | nr | 19.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
e | ridge tile |  | nr | 19.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
5 | Overlay existing 150mm insulation with 300mm quilt insulation to comply with Part 'L'. |  | m² | 5.03 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
6 | Strip off existing flat roof coverings and remove from site; prepare sub-structure; install high-performance, 3 layer built-up bitumen felt roof covering including primer, self-adhesive vapour barrier, tapered insulation, skirtings, fillets, welted drips, kerbs, edge trims, outlet gully linings, waterchecks, mastic pointing to chases, expansion joints, 'Ubiflex' flashings and soakers (or flashings & soakers of an equivalent specification'); flashings to stacks and abutments; all fixed in accordance with manufacturers instructions. | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
a | main roof |  | m² | 92.6055 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
b | bay window or porch roof |  | m² | 103.6815 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
c | pediments |  | m² | 103.6815 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
d | out-house roof |  | m² | 70 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
e | private balconies |  | m² | 48.75 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
f | staircase roofs |  | m² | 70 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
7 | code 4 lead collar to 100 diameter pipes |  | nr | 22.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Chimney - Major Repair
8 | raise 2 brick thick papapet by four facings courses in 4:1:1 mortar to match existing to accommodate new roof. Allow a PC sum of £380 per 1,000 bricks. |  | m | 52.35 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Chimney - Major Repair
9 a | 20mm thick, 2 coat Asphalt, on sheathing felt, sand-rubbed, width greater than 300mm, pitch less than 10 degrees, works subsequently covered, including 100mm thick insulation fully bonded in hot bitumen with metal-lined vapour control layer. | 24 | m² | 73.75 | 1770 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | repair existing asphalt including cutting out damaged areas, all preparation, priming and 2 coats of bitumen asphalt. |  | m² | 12 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
c | ditto to asphalt upstands or skirtings not exceeding 300 high. |  | m | 4.25 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
d | Liquid applied, non-slip coating system to existing asphalt to walkways and balconies; including preparation, primer, all kerbs, upstands, GRP trims, dressing in; all in accordance with manufacturers instructions. |  | m² | 33.735 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
10 | Apply 2 coats of solar paint to main & staircase roofs & balconies including all preparation and removal of any vegetation etc |  | m² | 5.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
11 | 350 x 350 x 25mm thick pedestrian tiles ('Spartan' or equivalent, approved specification) bonded in hot bitumen or PUR adhesive |  | nr | 12 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
12 | Install freestanding handrail system; 46.3 galvanised (to BS 729) steel guard rails including 800 x 150 x 20 thick base plates to all vertical standards at 2 metre centres, s.s. fixings, cleats and angles. |  | m | 34 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
13 a | Replace 19mm WBP plywood deck including taping strips to joints |  | m² | 19.72 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
b | Replace 50mm pre-screeded woodwool slabs with 18mm WBP plywood on treated battens, including taping strips to joints |  | m² | 18.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
14 | Replace 600 x 600 rooflight with triple-skin polycarbonate type including vented kerbs, fillets, capping, pvc trim to inner face, 19 x 150 exterior grade plywood to upstands and 3 layer waterproofing |  | nr | 522.9997 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
15 | Temporary roof, 3 metres high over pitched or flat with 1 metre overhang to all sides |  | m² | 23 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
16 | Replace pramshed roofing with single skin, 0.7mm thick, 34 deep/1000 wide box profiled, 'Plastisol' coated uPVC sheeting; including all fixings, foam filler/closure strips, waterproof sealant, flashings, preparation and any repairs to support structure and disposal of existing materials. |  | m² | 35.89 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
ROOFING ITEMS NOT COVERED BY LHS
1 | Removal of Existing Roof Coverings Tiles/slates, ridges, flashing, battens and felt inc de-nailing of rafters and all other components |  | m² | 5.45 |  | 130 | 708.5 | 100% | 708.5 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
2 | Redland 49 tiles - 22.5 - 35 deg pitche - 450mm or 600mm rafter cnetres. (Includes supply & fix membrane, battens & tiles) |  | m2 | 46.32 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
3 | Install Redland Cambrian Slates 25 deg - 90mm lap -610 x 305 (Includes supply & fix of membrane, battens and slates) |  | m² | 77.54 |  | 130 | 10080.2 | 100% | 10080.2 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
4 | Supply and install new treated softwood timber batten |  | m² | 2.47 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
5 | Graded battens |  | m2 | 5 |  | 130 | 650 | 100% | 650 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
6 | Extra cost for Redland Felt 400 2S |  | m2 | 3.5 |  | 130 | 455 | 100% | 455 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
7 | Extra over above for increased headlap due to pitch restrictions |  | m² | 2.81 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
8 | Wet Verge, abutments & eaves |  | m | 6.85 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
9 | Dry verge, abutments & eaves |  | m | 19.94 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
10 | Install Concrete ridge & hip components to concrete or resin tiled roofs | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a | Mortared vent ridge - Universal Angle. |  | m | 18.53 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | Dry Fix vent ridge - Universal Angle. |  | m | 31.98 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
c | Mortared /dry vent ridge - half round Angle. |  | m | 20.68 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
d | Dry Fix vent ridge - half round Angle. |  | m | 41.02 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
e | Mortared /dry vent ridge - Monoridge - Universal Angle. |  | m | 22.23 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
f | Dry Fix vent ridge - Monoridge - Universal Angle. |  | m | 37.64 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
g | Mortared /dry vent ridge - Monoridge - half round |  | m | 34.2 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
h | Dry Fix vent ridge - Monoridge - half round |  | m | 48.42 |  | 32 | 1549.44 | 100% | 1549.44 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
i | Mortared /dry vent ridge - third Universal Angle |  | m | 29.58 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
j | Dry Fix vent ridge - third Universal Angle |  | m | 38.21 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
k | Mortared /dry vent ridge - third round hip Angle |  | m | 28.28 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
l | Dry Fix vent ridge - third round hip Angle |  | m | 41.99 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
11 | Supply and install Inline/through ventilation tile. |  | No | 75.6 |  | 16 | 1209.6 | 100% | 1209.6 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
12 | Supply and install flexible air duct including adapting the existing ducting tu suit the vent |  | m | 45.6 |  | 16 | 729.6 | 100% | 729.6 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
13 | Install Redland Eaves Ventilation System |  | m | 29.5 |  | 47 | 1386.5 | 100% | 1386.5 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
14 | Install top edge ventilation abutment in accordance with BS 5250 |  | m | 29.5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
15 | Raking/cutting to valleys/hips |  | m | 10.97 |  | 48 | 526.56 | 100% | 526.56 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
16 | Supply and install Eaves insulation |  | m | 4.93 |  | 47 | 231.71 | 100% | 231.71 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
17 | Install ridge and hip components to natural slated roofs | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a | Mortared half-round clay ridge |  | m | 19.75 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | Dry Fix half-round clay ridge |  | m | 41.02 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
c | Mortared half-round concrete ridge |  | m | 18.47 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
d | Dry Fix half-round concrete ridge |  | m | 41.02 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
e | Mortared third-round clay ridge |  | m | 20.2 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
f | Dry Fix third-round clay ridge |  | m | 41.02 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
g | Mortared third-round concrete ridge |  | m | 19.18 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
h | Dry Fix third-round concrete ridge |  | m | 41.02 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
17 | Extra over for clipping/ double nailing to meet BS 15534 | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a | Double nailing individual tiles |  | m2 | 5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | Clipping of plain tiles |  | m2 | 5.5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
v | Clipping of interlocking tiles/Cambrian Slates |  | m2 | 6 |  | 130 | 780 | 100% | 780 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
18 | Code 5 lead covered wood ridge roll |  | m | 65.1514 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
19 | Ditto with manufactured lead replacement material |  | m | 28.0617 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
20 | Code 4 lead covered wood hip roll |  | m | 56.623 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
21 | Ditto with manufactured lead replacement material |  | m | 25.2267 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
22 | Cut & mitred hip with code 3 lead soakers |  | m | 49.6125 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
23 | Ditto with manufactured lead replacement material |  | m | 33.3283 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
24 | Abutments formed with lead soakers & cover flashings. | [5 empty] | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
25 | Stepped horizontal brickwork - Including cutting of chase in brickwork |  | m | 45.5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
27 | Ditto with manufactured lead replacement material |  | m | 27.3663 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
28 | Abutments formed with stepped lead flashings | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
29 | 33 15 - 40deg stepped horizontal brickwork 34 chased groove parallel to pitch Extra over chasing |  | m | 45.5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
30 | Ditto with manufactured lead replacement material |  | m | 21.325 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
31 | Chased groove parallel to pitch Extra over chasing to a minimum 25mm depth |  | m | 3.815 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
32 | Lead saddle abuttments | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
33 | Bossed lead saddle |  | No | 28.72 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
34 | Leadburned saddle |  | No | 34.6008 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
35 | Ditto with manufactured lead replacement material |  | No | 20.325 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
36 | Lead Lined Valley Gutter | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
37 | Supply & install valley boards, prepare & install 500mm wide lead valley. |  | m | 78 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
39 | Supply & install Redland Dry valley ( inc. valley board ) |  | m | 68.5 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
40 | supply & install valley boards, prepare and install 500mm wide lead valley. supply & install valley boards, prepare and install 650mm x 650mm lead saddle. |  | No | 45.841 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
41 | Ditto with manufactured lead replacement material |  | No | 27.4717 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
| General | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
42 | Cut tile and install Lead slate to external pipe up to 150mm |  | No | 53.83 |  | 2 | 107.66 | 100% | 107.66 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
43 | Replace Lead box gutter up to 1000mm wide inc T Penne joints including up stands |  | m | 197.72 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
44 | Ditto with manufactured lead replacement material |  | m | 70.7964 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
45 | Take up replace and make good flat & vertical code 5 lead covering |  | m² | 157.66 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
46 | Remove and replace lead chutes up to 1000mm girth connected to lead box gutter |  | No | 50.2795 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
47 | Ditto with manufactured lead replacement material |  | No | 43.7183 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
48 | Supply and fix tiles to vertical surfaces to include fire proofing |  | m² | 49.4512 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
49 | Racking cutting on roof coverings to valleys and hips |  | m | 11.3531 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
50 | Supply and fit galvanized steel hip iron to bottom of bedded hips |  | No | 2.757 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
51 | All necessary lead works to chimney stacks of 2 pots |  | No | 132.66 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
52 | All necessary lead works to chimney stacks of 4 pots |  | No | 216.604 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
53 | All necessary lead works to chimney stacks of 8 pots |  | No | 282.49 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
54 | Supply and fix lead secret gutters at all abutments up to a max 400mm girth |  | m | 44.9 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
55 | Supply and fix Redland Dry Bonding Gutter |  | m | 49.35 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
56 | Provide and fix counter battens on boarded roof. |  | m² | 2.38 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
57 | Supply and fix gas vent ridge, adaptor & blanking conversion pack excluding connection (flexi pipe) |  | No | 55.8146 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
58 | Remove and replace defective timber work 100mm x 50mm |  | m | 12.6649 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
59 | Reforming timberwork to lead roofing & gutters |  | m² | 28.8111 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
60 | Strip and replace pitched roofs on small porches or bay window roofs up to 3 m2 |  | No | 252.61 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
61 | Remove existing and supply and fix new Velux roof light up to 600 x 1000mm |  | No | 241.84 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
62 | Remove existing and supply and fix new Velux roof light up to 1600 x 1000mm |  | No | 273.28 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
63 | Form opening in existing pitched roof and supply and fix new Velux roof light up to 600 x 1000mm |  | No | 268.74 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
64 | Form opening in existing pitched roof and supply and fix new Velux roof light up to 1600 x 1000mm |  | No | 330.25 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
65 | Supply and install foil faced ne 90mm insulation board between existing rafters |  | m² | 9.32 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
66 | Pitched Roofing repairs | [5 empty] | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
67 | Remove existing broken tile/s.Supply and install new/reclaimed tile to match existing. |  | No | 5.12 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
68 | Remove existing broken slate or cement fibre tile/s.Supply and install new/reclaimed slate to match existing. |  | No | 7.2431 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
69 | Remove existing broken ridge/hip tile including cement mortar bedding and dispose, supply and install new ridge/hip tile to match existing or re-use existing if not damaged, bedded on new sand & cement mortar neatly pointed. |  | No | 11.171 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
70 | Remove deteriorated cement mortar from ridge, hip tiles, valley, verges or eaves, carefully re-point with new sand & cement mortar neatly pointed |  | m | 33.5834 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
71 | Carefully remove tiles/slates & undertile felt, set aside tiles for re-use, dispose of undertile felt, supply and install new undertile felt, battens and tiles. |  | m² | 32.7449 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
72 | Remove existing lead flashing including cement morter, rake out joint, supply and install new lead flashing ne 150mm neatly pointed with either sand & cement mortar or suitable lead mastic sealant. |  | m | 20.4324 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
73 | Remove existing lead flashing including cement morter, rake out joint, supply and install new lead flashing 150-350mm neatly pointed with either sand & cement mortar or suitable lead mastic sealant. NHF SOR for 225 plus difference in material cost in 225mm and 350mm |  | m | 60.04 |  | 28 | 1681.12 | 100% | 1681.12 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
74 | Remove existing lead flashing including cement morter, rake out joint, supply and install new lead flashing 350-800mm neatly pointed with either sand & cement mortar or suitable lead mastic sealant. NHF SOR for 225 plus difference in material cost in 225mm and 800mm |  | m | 80.27 |  | 6 | 481.62 | 100% | 481.62 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
75 | Carefully clear all moss, leaves, debris etc from existing gutters, lower to ground and dispose. |  | m | 3.4285 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
76 | Carefully remove existing damaged vent tile, supply and install new vent tile |  | No | 60.6759 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
77 | Minimun charge for minor repairs to street properties, includes all necessary labour, plant, materials and removal of waste from site. |  | No | 24.3852 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
78 | Other roofing associated works | [5 empty] | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
79 | Carefully remove the existing handrail and stanchions fixed to the deck. Make good deck in preperation for receiving new coverings. |  | m | 7.4488 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
80 | Install new freestanding handrail system, with stanchion feet set on a sacrificial layer of cap sheet loose laid beneath. |  | m | 38.9958 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
| Fascias | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
81 | Replace fascia and soffit boards in uPVC, including preparing sub-frame, 25mm strip ventilators, all drips, trims, seals, mastic pointing and scaffolding | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
a | a. not exceeding 200mm wide |  | m | 12.1875 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
b | b. not exceeding 300mm wide |  | m | 16.0875 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
82 | Replace barge boards in uPVC, not exceeding 300; including preparing sub-frame, trimming of rafter ends, all drips, trims, seals, mastic pointing, making good to undercloak, pointing up in sand-cement |  | m | 17.55 |  | 5 | 87.75 | 100% | 87.75 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
83 | Prepare & fix ventilator components to pre-installed PVC-U or timber soffits - Continuous 25mm strip - within soffit |  | m | 4.6167 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
84 | Prepare & fix ventilator components to pre-installed PVC-U or timber soffits - Continuous 25mm strip - over fascia |  | m | 4.8703 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
85 | Prepare & fix ventilator components to pre-installed PVC-U or timber soffits - Circular grilles - within soffit |  | No | 3.423 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
86 | Prepare & fix ventilator components to pre-installed PVC-U or timber soffits - Rectangular grilles - within soffit. |  | No | 4.5408 |  |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
| Pitched Roof Insulation | [8 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
87 | Overlay existing 150mm insulation with 300mm quilt insulation to comply with Part 'L'. |  | m² | 5.03 |  | 110 | 553.3 | 100% | 553.3 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
|  |  |  | SECTION TOTAL | 25338.5 |  | 21218.56 |  | 21218.56
CONCRETE REPAIRS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Prepare and clean all concrete surfaces by suitable mechanical means such as abrasive blast cleaning or equivalent to ensure cement laitance and surface contaminations are removed and all blowholes and honeycombed areas are exposed. | 50 | m² | 7.63 | 381.5 | 145 | 1106.35 | 100% | 1106.35 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
2 | Carry out visual inspection & sounding/hammer survey of all concrete surfaces. | 50 | m² | 2.98 | 149 | 145 | 432.1 | 100% | 432.1 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
3 | Carry out cover meter survey of all concrete surfaces | 50 | m² | 2.98 | 149 | 145 | 432.1 | 100% | 432.1 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
4 | Carry out carbonation depth testing on concrete surface, including breaking out concrete, removing dust and testing with phenolphthalein solution. Allow 2 tests per property. | 2 | nr | 0.98 | 1.96 | 2 | 1.96 | 100% | 1.96 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
5 | Break out defective concrete to expose reinforcement; clean to bright metal and apply one coat of Sika Mono-top 610 (or mortar of an equivalent specification) to a minimum of 1mm; after the first coat has set apply a second coat as a bonding bridge and, while still wet, apply Sika Mono-top 615 (or mortar of an equivalent specification) repair mortar using a 'placing' rather than a 'rendering' technique to ensure adequate compaction; float finish; all works to be in accordance with the manufacturers instructions. | [8 empty] | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
A | for surfaces to an average depth not exceeding 25mm | [8 empty] | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
1 | Surfaces not exceeding 0.01m² | 10 | nr | 0.98 | 9.8 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
2 | Surfaces over 0.01m² but not exceeding 0.05m² | 10 | nr | 1.95 | 19.5 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
3 | Surfaces over 0.05m² but not exceeding 0.10m² | 10 | nr | 2.925 | 29.25 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
4 | Surfaces over 0.10m² but not exceeding 0.25m² | 10 | nr | 3.9 | 39 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
5 | Surfaces over 0.25m² but not exceeding 0.5m² | 10 | nr | 4.875 | 48.75 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
B | Ditto but surfaces to an average depth over 25mm but not exceeding 50mm | [8 empty] | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
1 | Surfaces not exceeding 0.01m² | 10 | nr | 9.75 | 97.5 | 55 | 536.25 | 100% | 536.25 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
2 | Surfaces over 0.01m² but not exceeding 0.05m² | 10 | nr | 14.625 | 146.25 | 45 | 658.125 | 100% | 658.125 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
3 | Surfaces over 0.05m² but not exceeding 0.10m² | 10 | nr | 15.6 | 156 | 20 | 312 | 100% | 312 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
4 | Surfaces over 0.10m² but not exceeding 0.25m² | 10 | nr | 16.575 | 165.75 | 7 | 116.025 | 100% | 116.025 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
5 | Surfaces over 0.25m² but not exceeding 0.5m² | 10 | nr | 19.5 | 195 | 8 | 156 | 100% | 156 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
6 | Sika MonoTop 620 (or mortar of an equivalent specification) levelling mortar, trowel applied; 2 to 5mm thick at a consumption of not less than 4.0k/m²; the maximum thickness per coat is 5mm; finish by means of a damp sponge to give an even and uniform texture to the surface, all in accordance with manufacturers instructions |  | m² | 6.7 | 0 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
7 | To the overall prepared, repaired and unrepaired concrete surface, brush or roller apply one coat of SikaGard 552W Aquaprimer (or mortar of an equivalent specification) at a consumption rate of not less than 0.2 ltr/m² ; after a minimum of 4 hours and when the primer is completely dry, brush, spray or roller apply 2 coats of SikaGard 550W Elastic (or mortar of an equivalent specification) at a minimum material consumption of 0.38 litres/m² per coat to achieve a minimum total dry film thickness of 400 microns; minimum wet film thickness for a two coat application should be 375 microns per coat; all works to be in accordance with manufacturers instructions | 50 | m² | 11.75 | 587.5 | 15 | 176.25 | 100% | 176.25 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
OR
| Apply 3 coat SikaGard 550W Elastic (or mortar of an equivalent specification) at a minimum material consumption of 0.25 litres/m² per coat to achieve a total dry film thickness of 400 microns; minimum wet film thickness for a 3 coat application should be 250 microns per coat; all works to be in accordance with manufacturers instructions. |  | m² | 11.75 | 0 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete
|  |  |  | SECTION TOTAL | 2175.76 |  | 3927.16 |  | 3927.16
EXTERNAL REPIARS & DECORATIONS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
Brickwork
1 | Rake out joints in brickwork and re-point in 6:1 sand-cement mortar. | 10 | m² | 24 | 240 | 119 | 2856 | 100% | 2856 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
2 a | Remove chimney pots/terminals, take down stack not exceeding 1.5m², re-build in new facing bricks to match existing; point stack including parging flue or re-fixing flue liners; re-fix flashings and pots/terminals including flaunching. |  | nr | 260 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
b | Remove chimney pots/terminals, take down stack exceeding 1.5m², re-build in new facing bricks to match existing; point stack including parging flue or re-fixing flue liners; re-fix flashings and pots/terminals including flaunching. |  | m² | 165 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
3 | Rake out & re-point brickwork to chimney stack | 6 | m² | 28 | 168 | 5 | 140 | 100% | 140 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
4 | Replace chimney terminal and make good flaunching | 4 | nr | 45 | 180 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
5 | Earthenware 'mushroom' vent to existing chimney pot and make good flaunching |  | nr | 85 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
6 | Bonded bead insulation to cavity walls; including drilling of and making good to holes. |  | m² | 4 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
Cladding
7 | Remove timber/board cladding, prepare sub-frame and install uPVC cladding including all drips, trims, seals, DPM, mastic pointing, fixings, accessories, edgings. |  | m² | 18 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Cladding
Surface Finishes
8 | Hack off render, prepare and apply stabiliser and new 20mm, 2 coat 3:1 sand-cement render. | 20 | m² | 28 | 560 | 8 | 224 | 100% | 224 | Capital SOR ¦ External Redecoration ¦ External Decorations
9 | Make good to defective render, prepare surface and apply 2 coats of masonry paint. | 50 | m² | 4.5 | 225 | 145 | 652.5 | 100% | 652.5 | Capital SOR ¦ External Redecoration ¦ External Decorations
10 a | Make good to any brick or concrete surface and prepare & apply 2 coats of masonry paint. |  | m² | 4.5 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
b | ditto to previously painted cills/lintels/thresholds/brick plinths/concrete n.e. 300mm girth. |  | m | 3 | 0 | 1120 | 3360 | 100% | 3360 | Capital SOR ¦ External Redecoration ¦ External Decorations
11 a | Rub down or burn off any timber surface, fill, prime, 2 undercoats and 1 gloss coat to areas exceeding 300mm wide. | 8 | m² | 12 | 96 | 10 | 120 | 100% | 120 | Capital SOR ¦ External Redecoration ¦ External Decorations
b | ditto to isolated pramshed or garage door (both sides) and frame |  | m² | 12 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
c | ditto to general surfaces not exceeding 300mm girth - soffits/fascias, barge boards skirtings |  | m | 3 | 0 | 860 | 2580 | 100% | 2580 | Capital SOR ¦ External Redecoration ¦ External Decorations
12 a | Wire brush, zinc primer, 2 undercoats and 1 coat zinc phosphate paint ('Hammerite' or equivalent specification) to previously painted metal surfaces. |  | m² | 10 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
b | ditto to general surfaces not exceeding 300mm girth, including gutters/downpipes/svp's/rails/ducting. | 100 | m | 3 | 300 | 230 | 690 | 100% | 690 | Capital SOR ¦ External Redecoration ¦ External Decorations
Miscellaneous
13 | Steam clean to thoroughly clean off grease, dirt etc to staircase landings and floor areas including treads and risers. |  | m² | 3 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
14 | Replace pramshed door & frame including all ironmongery. |  | nr | 125 | 0 |  | 0 |  | 0 | Capital SOR ¦ LHS Environmental Works ¦ Pram Shed - Major Repair
15 | Take down, store and afterwards re-fix sign. |  | nr | 10 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
16 | Remove and subsequently re-fix satellite dish. | 3 | nr | 90 | 270 | 3 | 270 | 100% | 270 | Capital SOR ¦ TV Aerial Works ¦ Communal TV Aerials
17 | Remove and subsequently re-fix TV aerial. | 3 | nr | 90 | 270 | 3 | 270 | 100% | 270 | Capital SOR ¦ TV Aerial Works ¦ Communal TV Aerials
18 | Arrange for BT to replace telephone cable and line, including all fixings, to one property. | 3 | nr | 98 | 294 | 3 | 294 | 100% | 294 | Capital SOR ¦ TV Aerial Works ¦ Communal TV Aerials
19 | Isolate, unclip, re-fix electrical cabling to facilitate other works in isolated areas. | 3 | nr | 10 | 30 | 15 | 150 | 100% | 150 | Capital SOR ¦ TV Aerial Works ¦ Communal TV Aerials
20 | Remove water based staining to brickwork | 15 | m² | 7.5 | 112.5 | 15 | 112.5 | 100% | 112.5 | Capital SOR ¦ External Redecoration ¦ External Decorations
|  |  |  | SECTION TOTAL | 2745.5 |  | 11719 |  | 11719
ADDITIONAL ITEMS (not included in LHS document)
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Supply and fit smoke/heat detectors to communal areas |  | nr | 94.145 | 0 |  | 0 |  | 0 | Capital SOR ¦ Fire Safety Works ¦ Fire Alarm - Renewal
4 | Timbercare repairs to box sash timber windows including overhauling renew staff and parting beads, take out sashes and later rehang on appropriate sized new undyed plaited nylon sash cords, renew pocket pieces, wedge and cramp loose sash frames, oil pulleys, ease and adjust sashes, remove, refit or renew ironmongery, rake out and renew defective putty and mastic, touch up decorations externally and internally to match existing and remove waste and debris. |  | nr | 150 | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
5 | Overhaul external door and frame with fanlight complete, remove all ironmongery, piece out door, frame, and architraves where iron- mongery removed make good any damage, defects to timber, resecure glazing beads, and architraves if loose, rehang door on one and a half pair of butt hinges, ease and adjust, reglaze fanlight as necessary to BS 6262, touch up decorations to match existing and remove waste and debris. |  | nr | 111.82 | 0 | 4 | 447.28 | 100% | 447.28 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal
6 | External wall: Make safe to existing and supply and lay new facing bricks in one brick wall bedded and pointed in cement lime mortar (1:1:6) as the work proceeds. |  | sm | 173.3 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry
| Damp works: Investigate and rectify cause of damp to RHS of building at low level including any remedial measures such as warerproof render etc. |  | Ps | [6 empty] | Capital SOR ¦ Preliminaries ¦ Pre-works Inspections and Surveys
7 | Stucco detailing to portico and window surrounds: Apply 12mm cement and sand render (1:3) with waterproofing agent to external walls including ‘Decorative’ finish, dub out as necessary with cement and sand and all labours and remove waste and debris |  | sm | 41.24 | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
8 | Dormer: Remove existing and replace, including all associated works |  | Ps | 900 | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
10 | Cut out defective bricks an stitch in to match existing |  | Lm | 60.21 | 0 | 125 | 7526.25 | 100% | 7526.25 | Capital SOR ¦ External Redecoration ¦ External Decorations
11 | Supply and fit guard rail in steel to rear garden to prevent falls between levels . Fixed to ground. |  | Ps | 1500 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
12 | Supply anf fit handrail in steel to rear steps to prevent falls on stairs hazard (HHSRS). Fixed to wall |  | Ps | 1500 | 0 |  | 0 |  | 0 | Capital SOR ¦ External Redecoration ¦ External Decorations
13 | Rebuild steps to front in sandstone to match existing profile. Allow for covering in asphalt |  | Ps | 5000 | [5 empty] | Capital SOR ¦ Concrete Repairs ¦ Floor Construction - Major Repair - Concrete
14 | Paving slabs: Lift any size existing precast concrete paving flag, fill and compact hardcore to soft spots and rebed existing flag on 25mm bed of cement mortar (1:4) and point up joints. |  | nr | 8.56 | 0 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Floor Construction - Major Repair - Concrete
15 | Paving slabs: Lift remnants of existing 50mm standard size precast concrete paving flag, remove waste and debris, fill and compact hardcore to soft spots and lay new flag on 25mm bed of cement mortar (1:4), point up joints including any additional cutting and fitting to suit. |  | nr | 12.54 | 0 |  | 0 |  | 0 | Capital SOR ¦ Concrete Repairs ¦ Floor Construction - Major Repair - Concrete
16 | Scaffolding: Allow for bridge beam over rear extension | 1 | Ps | 750 | 750 | 1 | 700 | 100% | 700 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
17 | Design drawing for scaffolding. | 1 | Ps | 900 | 900 | 1 | 900 | 100% | 900 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
18 | Asbestos: Allowance for a refurbishment and demolition survey | 1 | Item | 250 | 250 | 1 | 250 | 100% | 250 | Capital SOR ¦ Preliminaries ¦ Asbestos Surveying
19 | Supply and install helibar fixings | 3 | m | 92.46 | 277.38 | 10 | 924.6 | 100% | 924.6 | Capital SOR ¦ External Redecoration ¦ External Decorations
20 | Install new lead roof covering |  | m2 | 157.57 | 0 |  | 0 |  | 0 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat
21 | Install lead flashing to dormer window |  | m2 | 181.8 | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
22 | Install lead flashing to roof parapet | 15 | Lm | 75.4 | 1131 | 15 | 1131 | 100% | 1131 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched
23 | Handball scaffolding tube, fixings etc through terraced property. | 1 | Item | 750 | 750 | 1 | 750 | 100% | 750 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
24 | Provisional Sum for FRA works to communal area. Includes for (flooring, electrics, fire doors, smoke detectors, fire stopping and decs) to measured on a property by property basis. | 1 | Item | 6000 | 6000 |  | 0 |  | 0 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping
25 | Additional extra over cost to allow for arched window heads. |  | Ps | 500 | 0 |  | 0 |  | 0 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed
26 | Extra over allowance to double board and poly bottom lift of scaffolding. | 20 | m | 8 | 160 | 20 | 160 | 100% | 160 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
27 | Allowance for man and van to dispose of waste | 1 | Item | 250 | 250 | 2 | 500 | 100% | 500 | Capital SOR ¦ Preliminaries ¦ Additional Waste Removal
28 | Supply and install french doors including fan lights |  | Ps | 2500 | 0 |  |  |  |  | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal
29 | Ladder access hatches | 4 | Nr | 13.37 | 53.48 | 4 | 53.48 | 100% | 53.48 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access
|  |  |  | SECTION TOTAL | 10521.86 |  | 13342.61 |  | 13342.61
ADDITIONAL ITEMS PICKED UP ON SITE
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | Install Redland Eaves Tray | 47 | Lm | 13.5 |  | 47 | 634.5 | 100% | 634.5 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched |  | Quote Received
2 | Extra cost for weather pointing | 124 | M2 | 19.08 |  | 124 | 2365.92 | 100% | 2365.92 | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry |  | Quote Received
3 | 315105 - TIMBER:EPOXY REPAIR NE 10MM:OVER 300MM | 98 | LM | 41.52 |  | 98 | 4068.96 | 100% | 4068.96 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
4 | 315109 - TIMBER:EPOXY REPAIR NE 25MM:NE 300MM | 90 | item | 37.85 |  | 90 | 3406.5 | 100% | 3406.5 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
5 | 315117 - TIMBER:EPOXY REPAIR NE 50MM:NE 300MM | 40 | item | 36.4 |  | 40 | 1456 | 100% | 1456 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
6 | 315119 - TIMBER:EPOXY REPAIR NE 75MM:NE 300MM | 45 | item | 37.85 |  | 45 | 1703.25 | 100% | 1703.25 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
7 | 322101 - DOOR:HIGH PERFORMANCE BACK DOOR | 1 | item | 548.95 |  | 1 | 548.95 | 100% | 548.95 | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal |  | NHF
8 | 515005 - PANE:REGLAZE 4MM CLEAR OR OBSCURE UPTO 1.00SM | 4 | item | 77.01 |  | 4 | 308.04 | 100% | 308.04 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
9 | 575001 - PUTTY:RENEW DEFECTIVE PUTTY | 105.5 | LM | 4.67 |  | 105.5 | 492.685 | 100% | 492.685 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | NHF
10 | Building Control fees | 2 | item | 445.4 |  | 2 | 890.8 | 100% | 890.8 | Capital SOR ¦ Preliminaries ¦ Building Control Application |  | Agreed - Market rate
11 | Allowance for labourer for manual handling to materials | 5 | item | 150 |  | 5 | 750 | 100% | 750 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched |  | Agreed - in lieu of hoist
12 | Roof up to 8m2: liquid roof | 2 | item | 1232 |  | 2 | 2464 | 100% | 2464 | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched |  | Quote Received
13 | Decorate detail up to 0.5LM long | 22 | item | 32.5 |  | 22 | 715 | 100% | 715 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | Quote Received
14 | Temporary roof tarpaulins due to asbestos removal | 1 | item | 337.5 |  | 1 | 337.5 | 100% | 337.5 | Capital SOR ¦ External Redecoration ¦ External Decorations
15 | Timber window undertake timber repairs x 2nr Windows and Overhaul. | 1 | item | 420.86 |  | 1 | 420.86 | 100% | 420.86 | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | Reasonable
16 | Pigeon Spikes | 48 | item | 18.9 |  | 48 | 907.2 | 100% | 907.2 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | Quote received
17 | cost for slate and half material | 90 | LM | 2.5 |  | 90 | 225 | 100% | 225 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | Quote received
18 | Extra cost for double slate material | 80 | LM | 5.75 |  | 80 | 460 | 100% | 460 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | Quote received
19 | Expansion joint rubber lead | 2 | Items | 90 |  | 2 | 180 | 100% | 180 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal |  | Quote received
20 | Aluminium Gutter | 44 | LM | 39.5 |  | 44 | 1738 | 100% | 1738 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal |  | Quote received
21 | Aluminium Down Pipe | 30 | LM | 36.5 |  | 30 | 1095 | 100% | 1095 | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal |  | Quote received
22 | Scaffold Adaptations for asbestos testing | 1 | Item | 500 |  | 1 | 500 | 100% | 500 | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access |  | Agreed previously
23 | Lead Testing | 1 | Item | 200 |  | 1 | 200 | 100% | 200 | Capital SOR ¦ Preliminaries ¦ Pre-works Inspections and Surveys |  | Agreed
|  |  |  | SECTION TOTAL | 0 |  | 25868.165 |  | 25868.165
INTERNAL WORKS
ITEM | DESCRIPTION OF WORKS | QUANTITY | UNIT | RATE | VALUE | Rescope Qty | Rescope Value | Claim % | Valuation Claim
1 | 435119 - SEALER:APPLY ONE COAT TO WALLS AND CEILINGS | 144 | No | 4.99 |  | 144 | 718.56 | 100% | 718.56 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
2 | 411121 WALL HACK REPLASTER DUB OUT IN PATCH | 7 | No | 48.97 |  | 7 | 342.79 | 100% | 342.79 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
3 | 4359AA - WALLS:ANTI-GRAFFITI FLAME RETARDENT COATINGS | 144 | M2 | 23.1 |  | 144 | 3326.4 | 100% | 3326.4 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
4 | 436203 - SKIRTINGS & DOOR FRAME | 91 | lm | 6.76 |  | 91 | 615.16 | 100% | 615.16 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal |  | NHF
5 | 436207 - DOOR:PREPARE PRIME PAINT 2 GLOSS METAL GLAZED | 5 | Item | 74.31 |  | 5 | 371.55 | 100% | 371.55 | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal |  | NHF
6 | 436203 - HANDRAIL AND SPINDLES | 296 | lm | 6.76 |  | 296 | 2000.96 | 100% | 2000.96 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
7 | 432507 - SHEET FLOORING:LAY NEW VINYL AND SUB-BASE | 23 | M2 | 44.73 |  | 23 | 1028.79 | 100% | 1028.79 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
8 | 432703 - SKIRTING:RENEW VINYL ETC OVER 1.0M | 66 | lm | 11.47 |  | 66 | 757.02 | 100% | 757.02 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
9 | 432903 - NOSING:SUPPLY AND FIX NOSING TO STEP | 33 | Item | 41.37 |  | 33 | 1365.21 | 100% | 1365.21 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
10 | 881001 - EMERGENCY LIGHTING:RENEW SELF CONTAINED FITTING | 4 | Nr | 68.96 |  | 4 | 275.84 | 100% | 275.84 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | NHF
11 | 881003 - EMERGENCY LIGHTING:RENEW EXIT SIGN | 4 | Nr | 96.2 |  | 4 | 384.8 | 100% | 384.8 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | NHF
12 | 872015 - SMOKE DETECTORS:INSTALL OPTICAL IONISATION SYSTEM | 4 | Nr | 104.54 |  | 4 | 418.16 | 100% | 418.16 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | NHF
13 | 872101 - HEAT DETECTOR:INSTALL | 4 | Nr | 95.03 |  | 4 | 380.12 | 100% | 380.12 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | NHF
14 | MAN - Radio interlink call point with smoke detector | 1 | Item | 105 |  | 1 | 105 | 100% | 105 | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | Agreed - market rate
15 | 432303 - FLOOR TILES:HACK UP VINYL TILES | 39.5 | m2 | 7.2 |  | 39.5 | 284.4 | 100% | 284.4 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
16 | Build box to stopcock from fire rated plasterboard,door and hinges and architrave | 1 | Item | 150 |  | 1 | 150 | 100% | 150 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | Agreed - market rate
17 | Complete rewire to light ring due to existing was not in permanent light | 1 | item | 300 |  | 1 | 300 | 100% | 300 | Capital SOR ¦ Electrical Installations ¦ Communal Lighting |  | Agreed - market rate
18 | 305103 - FLOORING:RENEW IN 6MM PLYWOOD | 23 | M2 | 20.2 |  | 23 | 464.6 | 100% | 464.6 | Capital SOR ¦ External Redecoration ¦ External Decorations |  | NHF
|  |  |  | SECTION TOTAL | 0 |  | 13289.36 |  | 13289.36
|  |  |  | TOTAL WORKS COST | 77432.004 |  | 102149.875 |  | 102149.875 |  | Capital SOR ¦ Scaffolding ¦ Scaffolding and Access |  | 18186.5 | 15848.5 | 15848.5
[11 empty] | Capital SOR ¦ Rain Water Goods ¦ Rainwater Goods - Renewal |  | 893 | 3013 | 3013
[11 empty] | Capital SOR ¦ Electrical Installations ¦ Communal Lighting |  | 0 | 300 | 300
[11 empty] | Capital SOR ¦ Lightning Protection ¦ Lightning Protection System - Renewal |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ Windows ¦ Windows - Renewal - Double Glazed |  | 20184.364 | 11856.295 | 11856.295
[11 empty] | Capital SOR ¦ Internal Dwelling Works ¦ Property Front Door - Renewal |  | 0 | 1433.99 | 1433.99
[11 empty] | Capital SOR ¦ Internal Dwelling Works ¦ Property Rear Door - Renewal |  | 0 | 548.95 | 548.95
[11 empty] | Capital SOR ¦ Roof Works ¦ Fascias and Soffits - Renewal |  | 643.5 | 0 | 0
[11 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Pitched |  | 25826 | 26198.06 | 26198.06
[11 empty] | Capital SOR ¦ Roof Works ¦ Primary Roof - Renewal - Flat |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ Roof Works ¦ Chimney - Major Repair |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ Concrete Repairs ¦ Building Walls - Major Repair - Concrete |  | 2175.76 | 3927.16 | 3927.16
[11 empty] | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Brick or Masonry |  | 588 | 5361.92 | 5361.92
[11 empty] | Capital SOR ¦ External Walls ¦ Building Walls - Major Repair - Cladding |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ External Redecoration ¦ External Decorations |  | 1570.88 | 29273.28 | 29273.28
[11 empty] | Capital SOR ¦ LHS Environmental Works ¦ Pram Shed - Major Repair |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ TV Aerial Works ¦ Communal TV Aerials |  | 864 | 984 | 984
[11 empty] | Capital SOR ¦ Fire Safety Works ¦ Fire Alarm - Renewal |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ Preliminaries ¦ Pre-works Inspections and Surveys |  | 0 | 200 | 200
[11 empty] | Capital SOR ¦ Concrete Repairs ¦ Floor Construction - Major Repair - Concrete |  | 0 | 0 | 0
[11 empty] | Capital SOR ¦ Preliminaries ¦ Asbestos Surveying |  | 250 | 250 | 250
[11 empty] | Capital SOR ¦ Fire Safety Works ¦ Fire Stopping |  | 6000 | 1563.92 | 1563.92
[11 empty] | Capital SOR ¦ Preliminaries ¦ Additional Waste Removal |  | 250 | 500 | 500
[11 empty] | Capital SOR ¦ Preliminaries ¦ Building Control Application |  | 0 | 890.8 | 890.8
[11 empty] | Capital SOR ¦ Asbestos Removal ¦ Asbestos Removal |  | 0 | 0 | 0
[13 empty] | 77432.004 | 102149.875 | 102149.875
0