## Inspections
IRN18003017: Leigham Court Road Highways Inspections Between 21.05.2022 and 21.05.2023
Activity | Date | Inspection Frequency Type | Description
Carriageway Inspection | 2022-06-24 | 1 Month | DEFECTS FOUND
Carriageway Inspection | 2022-07-27 | 1 Month | NO NEW DEFECTSFOUND
Carriageway Inspection | 2022-08-26 | 1 Month | NO NEW DEFECTS FOUND
Carriageway Inspection | 2022-09-27 | 1 Month | NO NEW DEFECTS FOUND
Carriageway Inspection | 2022-10-27 | 1 Month | NO NEW DEFECTS FOUND
Carriageway Inspection | 2022-11-30 | 1 Month | NO NEW DEFECTS FOUND
Carriageway Inspection | 2022-12-29 | 1 Month | NEW DEFECTS FOUND
Carriageway Inspection | 2023-01-26 | 1 Month | DEFECTS FOUND
Carriageway Inspection | 2023-02-28 | 1 Month | NEW DEFECTS FOUND
Carriageway Inspection | 2023-03-31 | 1 Month | NEW DEFECTS FOUND
Carriageway Inspection | 2023-04-27 | 1 Month | DEFECTS FOUND
Footway Inspection | 2022-06-06 | 1 Month | NO DEFECTS FOUND
Footway Inspection | 2022-07-05 | 1 Month | NO DEFECTS FOUND
Footway Inspection | 2022-08-01 | 1 Month | OBSERVED DEFECT
Footway Inspection | 2022-09-06 | 1 Month | OBSERVED DEFECT
Footway Inspection | 2022-10-04 | 1 Month | NO DEFECTS FOUND
Footway Inspection | 2022-10-12 | 6 Months | OBSERVED DEFECTS
Footway Inspection | 2022-11-02 | 1 Month | NO DEFECTS FOUND
Footway Inspection | 2022-12-05 | 1 Month | OBSERVED DEFECT
Footway Inspection | 2023-01-04 | 1 Month | OBSERVED DEFECTS
Footway Inspection | 2023-02-01 | 1 Month | NO DEFECTS FOUND
Footway Inspection | 2023-03-02 | 1 Month | OBSERVED DEFECTS
Footway Inspection | 2023-03-21 | 6 Months | OBSERVED DEFECTS
Footway Inspection | 2023-04-04 | 1 Month | OBSERVED DEFECTS
Footway Inspection | 2023-04-18 | 6 Months | OBSERVED DEFECTS
Footway Inspection | 2023-05-03 | 1 Month | OBSERVED DEFECTS

## Repair Works Orders
IRN18003017: Leigham Court Road Highways Completed Repair Works Orders Raised Between 21.05.2022 and 21.05.2023
L.A.Code | Priority | Defect | Location | Date Ordered | Date Completed | Description | Defect Description | Easting | Northing
195919 | C | SMF | OPP. 45 | 2022-06-17 | 2022-07-03 | SM/JS TAKE UP AND RENEW 0.6 X 0.6 CRACKED AND UNEVEN ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530369.18 | 172536.96
195921 | C | SMF | O/S WOODLAWNS COACH HOUSE | 2022-06-17 | 2022-07-10 | SM/JS RENEW 2M LOOSE AND DAMAGED GUARDRAIL TAKE UP AND RELAY 0.4 X 0.4 UNEVEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530426.09 | 172460.63
195922 | C | SMF | O/S WOODLAWNS COACH HOUSE | 2022-06-17 | 2022-07-06 | SM/JS RENEW ZEBRA CROSSING | STRUCTURAL MAINTENANCE FOOTWAY | 530429.15 | 172455.91
195924 | C | SMF | J/W CULVERHOUSE GARDENS | 2022-06-17 | 2022-07-04 | SM/JS TAKE UP AND RELAY 2 X 1.8M SUNKEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530632.25 | 172233.13
195925 | C | SMF | OPP 109 | 2022-06-17 | 2022-07-03 | SM/JS TAKE UP AND RELAY 1.2 X 1.2 SUNKEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530700.23 | 172194.69
195926 | C | SMF | OPP 113 | 2022-06-17 | 2022-07-03 | SM/JS TAKE UP AND RELAY 2.8 X 1.5 SUNKEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530719.17 | 172187.32
195927 | C | SMF | OPP 135 | 2022-06-17 | 2022-07-01 | SM/JS RENEW 0.2 X 0.1 BLOCK | STRUCTURAL MAINTENANCE FOOTWAY | 530850.9 | 172145
195930 | C | SMF | APPROX. 20M FROM J/W KNOLLYS ROAD | 2022-06-17 | 2022-07-01 | SM/JS TAKE UP AND RELAY 2.8 X 1.5 SUNKEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530907.28 | 172142.78
195931 | C | SMF | APPROX. 30M FROM J/W KNOLLYS ROAD | 2022-06-17 | 2022-07-01 | SM/JS 0.7 X 0.2 CONCRETE FILLET AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530890.37 | 172146.58
195932 | B | SMF | O/S 123 | 2022-06-17 | 2022-06-20 | SM/JS 1.2 X 0.1 CONCRETE FILLET AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530797.01 | 172171.1
195933 | C | SMF | OPP 56 | 2022-06-17 | 2022-07-01 | SM/JS TAKE UP AND RELAY LOOSE 0.4 X 0.4 SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530549.5 | 172325.39
195928 | C | SMF | 20M FROM J/W VALLEY ROAD | 2022-06-17 | 2022-07-01 | SM/JS TAKE UP AND RELAY 1.2 X 0.4 SUNKEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530897.27 | 172132.98
195929 | C | SMF | BY TRAFFIC LIGHTS J/W KNOLLYS ROAD | 2022-06-17 | 2022-07-01 | SM/JS TAKE UP AND RELAY 0.6 X 0.1 BLOCKS AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530922.98 | 172138.71
195934 | C | SMF | O/S 61 | 2022-06-20 | 2022-07-03 | SM/JS TAKE UP AND RELAY 1.2 M UNEVEN KERB | STRUCTURAL MAINTENANCE FOOTWAY | 530473.47 | 172416.33
196164 | C | SMC | OPP. STREATHAM CLOSE, O/S 12 | 2022-06-24 | 2022-07-09 | JS BREAK OUT AND LAY HRA, 1.8 X 0.8m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 530412.39 | 172482.04
196166 | C | SMC | OPP. 71 | 2022-06-24 | 2022-07-09 | JS BREAK OUT AND LAY HRA, 1.2 X 0.5m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 530493.89 | 172379.73
196167 | C | SMC | J/W VALLEY ROAD | 2022-06-24 | 2022-07-16 | JS BREAK OUT AND LAY HRA AROUND THAMES WATER COVER, 1.6 X 1.2m SCALING/CRACKING | STRUCTURAL MAINTENANCE CARRIAGEWAY | 530938.33 | 172123.47
196169 | C | SMC | OPP. J/W GLENNIE ROAD | 2022-06-27 | 2022-07-16 | JS BREAK OUT AND LAY HRA, 1.8 X 1.5m SUNKEN REINSTATEMENT PATCH | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531089.86 | 172015.18
196170 | B | SMC | O/S 166 | 2022-06-24 | 2022-07-10 | JS RENEW/REPLACE GULLY. GRATE PARTIALLY BROKEN AND OPEN | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531159.59 | 171933.98
196171 | B | SMC | O/S 224 ON PELICAN CROSSING | 2022-06-27 | 2022-07-02 | JS BREAK OUT AND LAY HRA, 1 X 1.2m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531177.63 | 171649.38
196172 | B | SMC | J/W ST JULIAN'S FARM ROAD | 2022-06-27 | 2022-07-02 | JS BREAK OUT AND LAY HRA, 1 X 1m C/WAY DEPRESSION | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531178.59 | 171614.94
196173 | B | SMC | O/S 309 | 2022-06-27 | 2022-08-09 | JS BREAK OUT AND LAY HRA, 1 X 1m AROUND 'LONDON BROADS' COVER POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531181.01 | 171498.35
196174 | B | SMC | O/S 325 | 2022-06-27 | 2022-06-28 | JS BREAK OUT AND LAY HRA, 0.75 X 0.5m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531203.7 | 171416.8
196165 | C | SMC | OPP. 67 | 2022-06-24 | 2022-07-09 | JS BREAK OUT AND LAY HRA, 1 X 0.5m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 530484.1 | 172390.35
196168 | C | SMC | OPP. J/W BROXHOLM ROAD | 2022-06-24 | 2022-07-09 | JS BREAK OUT AND LAY HRA, 0.6 X 0.6m POTHOLE | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531058.82 | 172054.81
196639 | C | SMF | J/W MOUNT NOD ROAD | 2022-07-05 | 2022-07-26 | JS/ RENEW CONCRETE FILLET AROUND CATV COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530612.48 | 172261.2
196937 | C | SMF | O/S ASH COURT | 2022-07-21 | 2022-08-09 | SM/ T/UP 1.2 X 0.6 ASP LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 531225.81 | 171231.42
196938 | B | SMF | O/S 1 TO 12 BENHURST COURT | 2022-07-21 | 2022-07-22 | SM/ T/UP AND R/LAY 0.8 X 0.4 LOOSE ROCKING SEF | STRUCTURAL MAINTENANCE FOOTWAY | 531188.37 | 171124.36
197154 | C | SMF | OPP 13-15 | 2022-08-02 | 2022-08-12 | SM/ REMOVE CROOKED POST UNUSED | STRUCTURAL MAINTENANCE FOOTWAY | 530305.73 | 172630.18
197220 | C | SMF | O/S 206 | 2022-08-04 | 2022-08-16 | LP- TAKE UP BROKEN AND UNEVEN PAVING AND RELAY DBM LEVEL TO MANHOLE COVER 1.2 X.6 ( F/W ) | STRUCTURAL MAINTENANCE FOOTWAY | 531180.47 | 171736.99
197819 | C | SMF | O/S 33A | 2022-09-07 | 2022-09-12 | SM/ T/UP 2.8 X 0.4 SEF LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 530340.01 | 172606.06
197951 | C | SMF | O/S 6 | 2022-09-21 | 2022-09-26 | SM/ T/UP 2 X 0.6 ASP LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 530334.97 | 172587.13
197952 | C | SMF | O/S 109 | 2022-09-21 | 2022-09-28 | SM/ R/NEW 2M GUARD RAIL | STRUCTURAL MAINTENANCE FOOTWAY | 530704.26 | 172203.73
197953 | C | SMF | O/S 107 | 2022-09-21 | 2022-09-28 | SM/ R/NEW 2M GUARD RAIL | STRUCTURAL MAINTENANCE FOOTWAY | 530696.13 | 172207.71
197954 | C | SMF | O/S 107 | 2022-09-21 | 2022-09-26 | SM/ R/NEW 0.4 X 0.4 SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530696.76 | 172206.8
198477 | C | SMF | OPP 210 | 2022-10-13 | 2022-11-01 | SM/ T/UP 0.8 X 0.4 SEF LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 531189.61 | 171716.47
198478 | C | SMF | OPP 206 | 2022-10-13 | 2022-11-01 | SM/ T/UP 0.4 X 0.4 SEF LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 531190.18 | 171734.9
198479 | C | SMF | OPP WINTON WAY | 2022-10-13 | 2022-10-14 | SM/ T/UP AND R/LAY 1.8 X 0.4 UNEVEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 531192.06 | 171142.37
198480 | C | SMF | O/S ALDER COURT | 2022-10-13 | 2022-11-01 | SM/T/UP 2.4 X 0.6 CRACKED LOOSE ASP LAY DBM TREE ROOTS | STRUCTURAL MAINTENANCE FOOTWAY | 531221.31 | 171206.71
198571 | C | SMF | OPP 282 | 2022-10-19 | 2022-10-24 | SM/ T/UP AND R/NEW 0.8 X 0.4 CRACKED SEF | STRUCTURAL MAINTENANCE FOOTWAY | 531222.75 | 171344.39
198763 | B | SMF | O/S 33A BY TREE | 2022-11-02 | 2022-11-04 | SM/ T/UP 5.2 X 0.4 DBM R/LAY WITH 5.2 X 0.4 SEF (13) NOT MARKED RECEIVED VIA EMAIL | STRUCTURAL MAINTENANCE FOOTWAY | 530339.89 | 172606.55
198764 | C | SMF | O/S 33A BY TREE | 2022-11-02 | 2022-12-09 | SM/ B/OUT AND LAY 1 X 1 DBM AROUND TREE NOT MARKED RECEIVED VIA EMAIL | STRUCTURAL MAINTENANCE FOOTWAY | 530340.27 | 172606
199036 | C | SMF | JCT STREATHAM HILL | 2022-11-15 | 2022-11-25 | SM/ T/UP AND R/LAY 0.6 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530299.14 | 172682.93
199300 | B | SMC | O/S 163 | 2022-11-25 | 2022-12-14 | LP- POTHOLE BY MANHOLE COVER .6 MTR ( C/W ) | STRUCTURAL MAINTENANCE CARRIAGEWAY | 530966.77 | 172119.12
199476 | C | SMF | JCT STREATHAM HIGH ROAD | 2022-12-06 | 2022-12-21 | SM/ T/UP AND R/LAY 1.2 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530294.44 | 172645.52
199779 | B | POT | O/S 71 | 2022-12-30 | 2023-01-04 | LP- POTHOLES X2= 1 X1 = 1 X1 ( C/W ) | POTHOLE | 530495.29 | 172379.04
199780 | B | POT | J/W MOUNT EARL GARDENS. | 2022-12-30 | 2023-01-04 | LP- POTHOLES X2= 1 X1 = 1 X1.5 ( C/W ) | POTHOLE | 530501.69 | 172369.38
199781 | B | POT | O/S 156 | 2022-12-30 | 2023-01-04 | LP- POTHOLES X2= 1 X1 = 1 X1 ( C/W ) | POTHOLE | 531124.87 | 171980.11
199845 | C | SMF | O/S 5 | 2023-01-05 | 2023-01-12 | SM/ T/UP AND R/LAY 0.3 X 0.3 LOOSE BLOCKS | STRUCTURAL MAINTENANCE FOOTWAY | 530306.61 | 172667.86
199846 | C | SMF | O/S ESTATE AGENTS | 2023-01-05 | 2023-01-12 | SM/ T/UP AND R/LAY 0.6 X 0.6 ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530299.67 | 172681.01
200024 | C | SMF | O/S 121 | 2023-01-12 | 2023-01-19 | SM/ T/UP AND R/LAY 0.4 X 0.4 LOOSE SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530790.33 | 172172.73
200035 | C | SMF | O/S 206 | 2023-01-12 | 2023-01-31 | LP- RAISE LEVEL OF FOOTWAY BY 60 MM TO TRY AND PREVENT RAIN FROM RUNNING OVER THE FOOTWAY AND INTO THE RESIDENTS PROPERTY CAUSING FLOOD ISSUES SUPPLY AND RELAY 4 MTRS OF EDGINGS ON BACK LINE OF FOOT | STRUCTURAL MAINTENANCE FOOTWAY | 531180.2 | 171735.81
200037 | C | SMF | O/S 206 | 2023-01-12 | 2023-02-04 | LP- BREAK OUT AND RELAY DBM 3 X 2.4 AS PART OF LA CODE 200035. | STRUCTURAL MAINTENANCE FOOTWAY | 531179.95 | 171735.36
200145 | C | POT | O/S 317 | 2023-01-19 | 2023-01-25 | LP- POTHOLE BY GULLY 1 MTR ( C/W ) | POTHOLE | 531187.82 | 171470.07
200204 | B | POT | O/S 166 | 2023-01-23 | 2023-02-07 | LP- RESET SUNKEN GULLY FRAME AND COVER AND REINSTATE POTHOLE AROUND GULLY 1 SQR MTR ( C/W ) | POTHOLE | 531159.74 | 171933.7
200205 | B | POT | O/S 232 | 2023-01-23 | 2023-01-26 | LP- POTHOLE 2 X.4 ( C/W ) | POTHOLE | 531174.74 | 171605.27
200206 | C | POT | O/S 234 | 2023-01-23 | 2023-01-31 | LP- POTHOLE 2 X.4 ( C/W ) | POTHOLE | 531174.71 | 171594.57
200207 | C | POT | J/W ETHERSTONE ROAD | 2023-01-23 | 2023-01-31 | LP- C/W PATCH SURFACE COURSE WEARING 3.5 X1.2 ( C/W ) | POTHOLE | 531174.73 | 171577.73
200208 | C | POT | O/S 297 | 2023-01-23 | 2023-01-31 | LP- POTHOLE .8 SQR MTR ( C/W ) | POTHOLE | 531174.46 | 171567.69
200310 | B | POT | O/S 156 | 2023-01-27 | 2023-01-31 | LP- POTHOLES X2= 1 X1 - 2 X1.2 ( C/W ) | POTHOLE | 531125.91 | 171979.36
200731 | C | POT | O/S 56 | 2023-02-16 | 2023-02-18 | LP- POTHOLES X2 =3 X1- 1 X .4 ( C/W ) | POTHOLE | 530545.32 | 172320.41
200732 | C | POT | O/S 22 | 2023-02-16 | 2023-02-17 | LP- POTHOLE .8 MTR ( C/W ) | POTHOLE | 530517.79 | 172352.25
200733 | C | POT | J/W MOUNT EARL GARDENS | 2023-02-16 | 2023-02-17 | LP- POTHOLES X 4 = .8 MTR = 1.5 X1= 3 X1 ( C/W ) | POTHOLE | 530505.03 | 172367.37
200734 | C | POT | J/W MOUNT EARL GARDENS | 2023-02-16 | 2023-02-20 | LP- POTHOLES X 4 = .5 X1( C/W ) | POTHOLE | 530507.05 | 172368.81
200735 | C | POT | O/S 18 | 2023-02-16 | 2023-02-17 | LP- POTHOLE 2 X.6 ( C/W ) | POTHOLE | 530476.82 | 172401.01
200736 | C | POT | O/S 16 ON ZEBRA XING | 2023-02-16 | 2023-02-20 | LP- POTHOLE .3 MTR ( C/W ) | POTHOLE | 530476.82 | 172401.01
200737 | C | POT | O/S ST ALBANS CLOSE | 2023-02-16 | 2023-02-20 | LP- POTHOLES X2 = 1.5 X .3 = .5 X .3 ( C/W ) | POTHOLE | 530405.96 | 172489.29
200738 | C | POT | O/S 193 | 2023-02-16 | 2023-02-18 | LP- POTHOLES X2 = 3 X1.2 = 2 X .4 ( C/W ) | POTHOLE | 531007.82 | 172094.47
200739 | C | POT | O/S CAREWHOUSE | 2023-02-17 | 2023-02-25 | LP- POTHOLE X2 = .8 MTR X 2 ( C/W ) | POTHOLE | 531057.18 | 172057.84
200922 | C | POT | J/W VALLEYFIELD ROAD | 2023-03-01 | 2023-03-06 | LP- C/W PATCH 1.5 X1 | POTHOLE | 531222.42 | 171321.01
200924 | C | SMF | O/S 282 | 2023-03-01 | 2023-03-11 | LP- RELAY UNEVEN SEF PAVING 1.6 X 1.6 ( F/W ) | STRUCTURAL MAINTENANCE FOOTWAY | 531211.72 | 171347.59
201013 | C | SMF | SIDE OF ESTATE AGENTS JCT STREATHAM HIGH RD | 2023-03-03 | 2023-03-13 | SM/ T/UP AND R/LAY 0.6 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530292.21 | 172647.61
201014 | C | SMF | OPP 13-15 BUS SHELTER | 2023-03-03 | 2023-03-13 | SM/ T/UP AND R/LAY 0.6 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530305.02 | 172633.47
201330 | C | ATM | WHOLE ROAD | 2023-03-16 | 2023-03-27 | LP- REFRESH ALL 20 MPH ROUNDELS X 17 ( C/W ) | AIDS TO MOVEMENT | 530467.74 | 172416.02
201489 | C | SMF | JCT STREATHAM HIGH RD | 2023-03-22 | 2023-04-09 | SM/ T/UP AND R/NEW 0.6 X 0.6 ASP SIDE OF ESTATE AGENTS | STRUCTURAL MAINTENANCE FOOTWAY | 530292.86 | 172646.47
201490 | C | SMF | O/S STREATLEIGH CRT | 2023-03-22 | 2023-04-09 | SM/ T/UP AND R/LAY 0.6 X 0.5 UNEVEN ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530308.17 | 172626.49
201491 | C | SMF | BEHIND BUS SHELTER OPP 13-15 | 2023-03-22 | 2023-04-09 | SM/ T/UP AND R/LAY 1.2 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530306.21 | 172630.49
201492 | C | SMF | O/S 6 DORCHESTER COURT | 2023-03-22 | 2023-04-09 | SM/T/UP AND R/LAY 0.6 X 0.4 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530363.16 | 172545.44
201493 | C | SMF | OPP 45 O/S DORCHESTER COURT | 2023-03-22 | 2023-03-27 | SM/ B/OUT AND R/LAY 1.3 X 0.9 DBM UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530371.14 | 172533.9
201494 | C | SMF | O/S 60 | 2023-03-22 | 2023-03-27 | SM/ B/OUT AND LAY 2.3 X 0.5 1.6 X 0.3 1.5 X 0.5 0.5 X 0.5 DBM UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530555.96 | 172303.53
201495 | C | SMF | O/S 62 | 2023-03-22 | 2023-03-27 | SM/ B/OUT AND LAY 0.5 X 0.4 DBM UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530563.06 | 172296.47
201496 | C | SMF | JCT CULVERHOUSE GARDENS | 2023-03-22 | 2023-04-09 | SM/ 0..9 X 0.1 CONCRETE FILLET AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530631.45 | 172232.17
201497 | C | SMF | O/S 78A | 2023-03-22 | 2023-03-27 | SM/ B/OUT AND LAY 2 X 0.7 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 530657.15 | 172214.58
201498 | C | SMF | O/S 80 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND LAY 3.3 X 0.9 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 530665.37 | 172209.65
201499 | C | SMF | O/S 80 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND LAY 1.6 X 0.9 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 530666.22 | 172208.86
201500 | C | SMF | O/S 80 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND LAY 1.3 X 0.9 DBM UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530665.94 | 172209.2
201501 | C | SMF | O/S 80 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND LAY 1.4 X 0.6 DBM UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530665.76 | 172208.64
201502 | C | SMF | OPP 115 | 2023-03-22 | 2023-04-12 | SM/ B/OUT AND R/NEW 1.5 X 0.6 BROKEN CONCRETE UNEVEN F/WAY | STRUCTURAL MAINTENANCE FOOTWAY | 530741.39 | 172177.9
201503 | C | SMF | OPP 139 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND LAY 2.3 X 0.6 DBM 1.9 X 0.9 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 530870.93 | 172140.38
201504 | C | SMF | OPP LEITHCOTE PATH | 2023-03-22 | 2023-04-11 | SM/ 0.9 X 0.1 CONCRETE FILLET AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 530876.38 | 172149.36
201505 | C | SMF | OPP 56 | 2023-03-22 | 2023-04-11 | SM/ T/UP AND R/LAY 0.4 X 0.4 UNEVEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530549.19 | 172326.25
201506 | C | SMF | OPP 12 | 2023-03-22 | 2023-04-14 | SM/ B/OUT AND R/NEW 0.8 X 0.3 CONCRETE | STRUCTURAL MAINTENANCE FOOTWAY | 530415.61 | 172489.6
201815 | C | ATM | WHOLE ROAD | 2023-03-29 | 2023-03-27 | LP- EXTRA 20 MPH X4 | AIDS TO MOVEMENT | 530822.56 | 172157.17
201939 | C | POT | S/O ESSO ETROL STATION | 2023-04-03 | 2023-05-07 | LP- POTHOLE 1 X1 NOT SPRAYED UP AS ROAD SURFACE WET ( C/W ) | POTHOLE | 530965.12 | 172115.6
201940 | C | POT | O/S ST PETERS CHURCH | 2023-04-03 | 2023-05-07 | LP- POTHOLE 1 X1 NOT SPRAYED UP AS ROAD SURFACE WET ( C/W ) | POTHOLE | 530965.12 | 172115.6
201943 | C | POT | J/W ETHERSTONE ROAD | 2023-04-03 | 2023-05-07 | LP- POTHOLES X4 = 4 X 1 X1 NOT SPRAYED UP AS ROAD SURFACE WET ( C/W ) | POTHOLE | 531174.29 | 171577.19
201944 | C | POT | O/S NORMINGTON COURT | 2023-04-03 | 2023-05-07 | LP- POTHOLE 1 X1 NOT SPRAYED UP AS ROAD SURFACE WET ( C/W ) | POTHOLE | 531197.95 | 171430.16
202029 | C | SMF | JCT STREATHAM HIGH RD | 2023-04-05 | 2023-04-22 | SM/ T/UP AND R/NEW 1.2 X 0.6 CRACKED LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530295.14 | 172644.91
202030 | C | SMF | OPP 13-15 BEHIND BUS SHELTER | 2023-04-05 | 2023-04-22 | SM/ T/UP AND R/LAY 1.2 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530300.28 | 172639.49
201988 | C | POT | O/S 58 | 2023-04-05 | 2023-05-11 | LP- POTHOLE 1 X1 ( C/W ) | POTHOLE | 530553.55 | 172312.88
201989 | C | POT | O/S 56 | 2023-04-05 | 2023-05-11 | LP- POTHOLES X2 = 3 X .8 - .4 MTR ( C/W ) | POTHOLE | 530544.68 | 172320.13
201990 | C | POT | O/S 22 | 2023-04-05 | 2023-05-12 | LP- POTHOLES X3 = 2.5 X .6 - 1 X1 - 1X1 ( C/W ) | POTHOLE | 530518.55 | 172349.93
201991 | C | POT | J/W MOUNT EARL GDNS | 2023-04-05 | 2023-05-13 | LP- POTHOLES X3 = 1 X1 - 2 X .4 - .5 MTR ( C/W ) | POTHOLE | 530506.36 | 172370.19
201992 | B | POT | OPP 69 | 2023-04-05 | 2023-04-06 | LP- POTHOLE 5 X 1 ( C/W ) | POTHOLE | 530489.56 | 172384.43
201993 | C | POT | OPP 67 | 2023-04-05 | 2023-05-13 | LP- POTHOLE 2 X 1 ( C/W ) | POTHOLE | 530485.25 | 172390.59
201994 | C | POT | O/S 14 | 2023-04-05 | 2023-05-13 | LP- POTHOLE 2 X .6 ( C/W ) | POTHOLE | 530431.19 | 172458.28
201995 | C | POT | O/S 12 G | 2023-04-05 | 2023-05-13 | LP- POTHOLE 1 X1 ( C/W ) | POTHOLE | 530417.89 | 172474.35
202336 | C | SMF | O/S 274 | 2023-04-19 | 2023-05-09 | SM/ B/OUT AND LAY 2.2 X 2.2 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 531204.66 | 171387.48
202337 | C | SMF | O/S 274 | 2023-04-19 | 2023-05-09 | SM/ B/OUT AND LAY 2.3 X 2 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 531204.32 | 171388.29
202338 | C | POT | JCT NORMINGTON CLOSE | 2023-04-19 | 2023-05-19 | SM/ B/OUT AND LAY 1.2 X 0.9 HRA POTHOLE | POTHOLE | 531197.28 | 171433.38
202339 | C | SMF | O/S 194 | 2023-04-19 | 2023-05-13 | SM/ T/UP AND R/LAY 1.4 X 0.4 SUNKEN SEF /BLOCKS T/UP AND R/NEW 0.4 X 0.4 CRACKED SEF MAKE EVEN WITH COVER. | STRUCTURAL MAINTENANCE FOOTWAY | 531180.59 | 171796.69
202340 | C | SMF | O/S 176 | 2023-04-19 | 2023-05-09 | SM/ B/OUT AND LAY 4.3 X 0.4 DBM UNEVEN CROSSOVER | STRUCTURAL MAINTENANCE FOOTWAY | 531173.43 | 171891.7
202341 | C | SMF | O/S 168 | 2023-04-19 | 2023-05-13 | SM/ 0.6 X 0.2 CONCRETE FILLET AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 531161.12 | 171927.38
202342 | C | SMF | O/S CAREW HOUSE | 2023-04-19 | 2023-05-09 | SM/ B/OUT AND LAY 1.8 X 0.7 DBM | STRUCTURAL MAINTENANCE FOOTWAY | 531056.02 | 172052.25
202343 | C | SMF | O/S MOUNTVIEW LEIGHAM CLOSE | 2023-04-19 | 2023-05-13 | SM/ T/UP AND R/LAY 0.4 X 0.4 LOOSE SEF | STRUCTURAL MAINTENANCE FOOTWAY | 530995.28 | 172096.9
202344 | C | SMF | O/S 199 | 2023-04-19 | 2023-05-17 | SM/ T/UP AND R/LAY 3.6M UNEVEN KERB | STRUCTURAL MAINTENANCE FOOTWAY | 531024.48 | 172092.13
202345 | C | SMF | O/S 199 | 2023-04-19 | 2023-05-17 | SM/ T/UP AND R/LAY 4.9M UNEVEN KERB | STRUCTURAL MAINTENANCE FOOTWAY | 531026.07 | 172091.07
202346 | C | SMF | OS 199 | 2023-04-19 | 2023-05-17 | SM/ T/UP AND R/LAY 2.2M UNEVEN KERB | STRUCTURAL MAINTENANCE FOOTWAY | 531019.71 | 172095.34
202347 | C | SMF | O/S 273 | 2023-04-19 | 2023-05-13 | SM/ T/UP AND R/LAY 1.6 X 0.4 UNEVEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 531189.96 | 171728.26
202349 | C | SMF | OPP 276 | 2023-04-19 | 2023-05-14 | SM/ T/UP AND R/LAY 1 X 0.4 SUNKEN SEF R/LAY 0.4 X 0.4 SUNKEN LOCKS AROUND COVER | STRUCTURAL MAINTENANCE FOOTWAY | 531216.41 | 171386.68
202350 | C | SMF | OPP 290 | 2023-04-19 | 2023-05-14 | SM/ R/NEW 1 X CONCRETE BOLLARD | STRUCTURAL MAINTENANCE FOOTWAY | 531227.85 | 171266.03
202420 | C | SMF | CLS TO BUS STOP OPP SYCAMORE COURT | 2023-04-20 | 2023-05-15 | SM/ T/UP AND R/LAY 2 X 0.4 UNEVEN SEF | STRUCTURAL MAINTENANCE FOOTWAY | 531188.98 | 171124.68
202565 | A | SMC | J/w glennie rd / outside& oppo st Peters church | 2023-04-28 | 2023-04-27 | KW/ AS PER TELEPHONE CONVERSATION PLEASE MAKE IT SAFE FOUR DEEP POTOLE OUTSIDE ST PETERS CHURCH AND SEVEN POTHOLES OPPOSITE TO THE CHURCH | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531103.52 | 172006.54
202812 | C | SMF | O/S KINGSLEIGH FOLKARD AND HAYWARD | 2023-05-04 | 2023-05-21 | SM/ T/UP AND R/LAY 0.6 X 0.6 LOOSE ASP | STRUCTURAL MAINTENANCE FOOTWAY | 530300.94 | 172679.26
202813 | C | SMF | O/S 5 | 2023-05-04 | 2023-05-21 | SM/ T/UP AND R/LAY 0.4 X 0.2 LOOSE BLOCKS | STRUCTURAL MAINTENANCE FOOTWAY | 530308.04 | 172666.53
203068 | B | SMC | JCT WINTON WAY | 2023-05-11 | 2023-05-12 | SM/ T/UP AND R/LAY 0.5M DISLODGED KERB | STRUCTURAL MAINTENANCE CARRIAGEWAY | 531213.37 | 171133.88